## 09_Call#3_Indicators
ANNEX I PROJECT 09_CALL#3 Biosphere Reserves: Sustainable Territories, Resilient communities
b) Indicators
Activity ID | Name of Activity | Beginning Date | Date Order | Description | Target Audience | Executing Entity | Indicator | Unit | Target | Verification Source
1 | Collection and organization of information related to the nomination of all Biosphere Reserves (BR) | 2020-11-12 | 2021-04-30 | Collection, compilation and systematisation of bibliographic and cartographic information that led to the creation of the 11 Biosphere Reserves (BRs) in order to identify the objectives and specificities of the territories, providing a baseline framework for the Sustainable Development Plans (SDP). The collection will be carried out through direct contact with each of the management units of the BRs, using one of the tools defined in the Participatory Model and will provide data to the project databases. This activity includes a “thinking tank” integrating international participants that will follow-up the development of the project which will allow consultation and exchange of experiences with different realities of the World Network of Biosphere Reserves (WNBR), thus reinforcing the potential for cooperation between BRs in the different MAB networks. This group includes BR managers from Spain, Chile, São Tomé and Príncipe, Mozambique, Guinea-Bissau, Mexico, Cape Verde, among others. | BR Managers | QP and other partners | Edited Report | Nº | 1 | Diagnostic Report
2 | Survey of existing BR action plans, objectives and priorities | 2020-11-12 | 2021-04-30 | Compilation of all existing cartographic and bibliographic information about BRs, from its inception to the present. All information concerning the protected areas corresponding to the core and buffer zones of each BR will be compiled, including their sector plans. The aim of the activity is to learn what is done and to evaluate the importance of the implementation of the planned actions, as well as any constraints, for the local community and BR managers. This activity is complementary to Activity 1 and should be linked with actions, after listening to managers, local agents and the local community, among others. The activity will provide data to the project databases. This activity includes local presentation of the project in BRs. | BR managers Local agents/players Local Community | QP and other partners | Edited Report | Nº | 1 | Diagnostic Report
3 | Framing the geostrategic context of BR in existing UNESCO BR networks | 2021-01-01 | 2021-03-31 | The activity aims to analyse the geostrategic context in which each BRs fits into, in terms of thematic and geographical networks, national and international, and the analysis of its strategic reference framework, in particular the orientations and policies related to conservation and sustainability, and Programs in place with an impact on each BR. It will also be essential to identify the group of entities with jurisdiction in the different territories covered by BRs. | BR Managers National MAB Committee | QP | Edited Report | Nº | 1 | Geostrategic Context Report
4 | History of BR | 2020-11-12 | 2022-11-01 | Collection and organisation of content associated with the historical path and the process of affirmation and impact of each Reserve from local and national archives and libraries (e.g. Archive from RTP-RDP, Film library, Press, Documentation in each Reserve). Development and publication of a book on the history of the Reserves considering the various contexts evoked, among others, public and local policies for the environment, the importance, meaning and impact of the UNESCO classification. | BR Managers General public | NOVA FCSH and other partners | Publications | Nº | 1 | Activity Report
5 | Elaboration of a database management plan: FAIR data - open access | 2020-11-12 | 2021-04-30 | Definition of a data management plan that specifies the methodologies and parameters of creation, collection, storage, organisation, deposit, description, documentation and access to data for the whole project, following best practices, pursuing open access purposes and in strict compliance with the FAIR principles (Findable, Accessible, Interoperable, Reusable). The results of the work carried out, the information collected and the research carried out, which nature and content could allow, will be disseminated (where possible in open access) and preserved; knowledge about BRs should be expanded and shared with society in general; the data collected should be made available, making it possible to reuse them for scientific and cultural purposes. The plan will follow internationally defined standards and models, highlighting the use of the DMP online form Digital Curation Centre. | BR Managers Scientific Community | NOVA FCSH and other partners | Availability of the Data Management Plan | Nº | 1 | Website
6 | Auscultation / Perception and identification of heritage | 2020-11-12 | 2021-04-30 | Listening about the perception, identification and characterisation of the cultural and natural vernacular heritage directed to the Reserves and local entities, through the construction and application of surveys in the initial phase of implementation of the project and in its final phase. | BR managers Communities and local partners | NOVA FCSH and other partners | Surveys applied | Nº | 300 | Analysis Report
7 | Development of the Sustainable Development Plan (SDP) concept for BR | 2021-03-01 | 2021-05-31 | This activity is dedicated to the design of the SDPs development model, starting from a benchmarking analysis of existing SDPs in order to stabilise a structure, contents and methodologies for the SDPs of the 11 BRs, taking advantage of the best that is done in the UNESCO Biosphere Reserves Networks, allowing to innovate and focus the SDPs on the most pressing issues today (efficient use of resources, sustainable consumption, preservation of biodiversity and landscapes, mitigation and adaptation to climate change and other environmental, health risks, etc.). In addition to being related to Activity 54, betting on the exchange of experiences with partner countries in this application, the result of the activity will be approved under Activity 9. | BR Managers UNESCO Network of Biosphere Reserves | QP and other partners | SDPs consulted | Nº | 10 | Report on the Concept of SDPs
8 | Development of the participatory planning methodology for the SDP | 2021-05-01 | 2021-07-31 | The activity is assumed as a strategic tool for the diagnosis and production of knowledge, for community development and for the training of the entities and population involved, among others. The methodology to be implemented will be linked with the guidelines established by the UNESCO MAB Program Strategy (2015-2025), the Lima Action Plan (2016-2025) and the Portuguese Action Plan for the Portuguese BRs network (2018-2025), with the existing and ongoing participatory activities in the BRs, but will be designed mainly focused on the expected results of the SDPs and will be cross-cuting to the 11 BRs. The National MAB Committee and the main local players will follow-up the creation of a specialised Focus Group, the development of surveys aimed at different target audiences, which will promote a program of meetings to discuss and follow-up the plans in each BR. The activity is linked with the remaining activities of characterisation and participatory involvement. | BR Managers/technicians Local agents/players Resident population/visitors Central Administration/Local Power ONG Scientific/school/artistic community General population | QP and other partners | Developed methodology | Nº | 1 | Participatory Model Report
9 | Consultation and validation of the methodological structure for the SDP | 2021-08-01 | 2021-09-30 | Once stabilised the methodological proposal of the SDPs (with the identification of the specificities of each SDP and organisation of development and participation mechanisms) and following a transparent and participatory process, it will be submitted for approval by the Advisory Committee, implementing the Participatory Model and promoting the legitimacy of the process. | Supervisor Committee | QP | Assent | Nº | 1 | Report on the Structure of the SDPs
10 | Digital Infrastructure - distributed management model | 2021-01-01 | 2021-06-30 | Creation of the systems architecture and respective functioning and governance model - distributed type - of digital infrastructure associated with biosphere reserves, comprising the following elements: A. BRs network presentation and information portal - internal and external promotion B. dashboard - graphical interface providing quick views of relevant key performance indicators (KPIs) - namely resulting from sustainability plans C. data infrastructure - integration of content databases and linkage with other infrastructures (e.g. GBIF, PRISC) | BR managers National MAB Committee | NOVA FCSH and other partners | Edited Report | Nº | 1 | Guidance Report/Handbook of procedures
11 | Digital Infrastructure - Biosphere Reserves website | 2020-11-12 | 2023-05-11 | Creation of website for presentation, enhancement and promotion of biosphere reserves as a whole - beta version in month 6 and final version on the deadline. It will aggregate the detailed information and the services provided by the reserves in its various domains: historical and heritage characterisation; ecosystem services; online stores of Biosphere Reserves; guidebooks and cultural and scientific paths in virtual format, with georeferencing; network of friends of Reserves - Biokeepers. It will also gather the information and make available the contents produced within the scope of the project. Includes programming and development of website/digital platform with custom applicational logic (database integration; webshop; APIs for integration with external services/entities), including front-end and back-end programming; testing; support and maintenance. | BR managers General public Tourism Scientific Community | NOVA FCSH and other partners | Website Launch | Nº | 1 | Website
12 | Digital infrastructure - Indicators management dashboard | 2020-11-12 | 2023-05-11 | Adoption of a Business Intelligence (BI) tool that allows to gather, produce and explore automatically indicators that support integrated management and decision making for all biosphere reserves. A collection of indicators (via a dashboard) will be made publicly available, which will allow the follow-up, integrated monitoring and impact assessment of the sustainable development model implemented. It links with measures relating to the conception of the system of indicators for sustainable development. | BR Managers General public | NOVA FCSH and other partners | Availability of dashboard indicators | Nº | 1 | Website
13 | Digital Infrastructure - Research Data Catalogue | 2021-05-01 | 2023-05-11 | Creation of a catalogue aggregating the set of existing research data on biosphere reserves, facilitating access to consolidated and existing information in other repositories and data sources. It will be developed in conjunction with the existing scientific research infrastructures in Portugal and other relevant entities/holders of content of this nature. | BR Managers Scientific Community | NOVA FCSH and other partners | Created online catalogue | Nº | 1 | Website
14 | Digital guides to cultural and natural heritage of the Biosphere Reserves | 2021-01-01 | 2023-01-30 | Mapping and characterisation of the cultural and natural heritage associated with each Reserve and research development with archives, libraries, other local and national resources (documentation, objects, photographs and other collections). Organisation, treatment and production of content for promotion in the platforms and channels of the project, highlighting the creation of guidebooks of the natural heritage of BRs. The results of the activity in conjunction with the actions related to the preparation and development of the SDPs, as well as the preparation of Tourist Roadmaps for the Portuguese Biosphere Reserves. | BR Managers Communities and local partners Scientific Community General public | NOVA FCSH | Guidebooks made | Nº | 15 | Website or Activity Report
15 | Mapping the BR ecosystem diversity | 2020-11-12 | 2021-04-30 | For each biosphere reserve, mapping of the existing ecosystems using geographic information systems and satellite images (Landsat and Sentinel) will be carried out. This approach will allow stratification of the three areas that constitute biosphere reserves and build Normalized difference vegetation indexes (NDVI), which will be used as proxies of the structural diversity of habitats and which in turn are proxies of biodiversity. | BR Managers Local Owners and Communities | CFE-UC | Maps of composition of ecosystems/habitats | Nº | 11 | Activity Report / Website
16 | Identification of potential Ecosystem Services (ES) associated with ecosystems | 2020-12-01 | 2021-05-31 | Identification of the potential provision ES will be carried out following a spatial landscape scale approach in order to determine spatial patterns and the overlapping (“stacking” concept) of the multiple services and functions of ecosystems, assessing their diversity and spatial heterogeneity in the three zones that makes up each BR. The evaluation of the potential provision ES will follow the analytical structure of the MAES and CICES, adjusted to the IPBES “Nature's contribution to people (NCP)” concept and will focus on indicators identified as relevant to map the ES. Thus, this task will assess the potential of each of the biosphere reserves in the provision of biotic and non-biotic, regulatory, social and cultural products and services, as well as identify the potential for the provisioning of endogenous natural resources. | BR Managers Local Owners and Communities | CFE-UC in conjunction with University of Bergen | List of potential ecosystem services | Nº | 11 | Activity Report
17 | Analysis of the dynamics of the socio-economic sector | 2021-01-01 | 2021-10-31 | The activity aims to update the strategic diagnostic information on the economic system existing in Portuguese BRs (based or with significant activity in these spaces) and relevant to the formulation of sustainable development strategies, particularly, in the valorisation of specific resources and tourism. Starting from repertoires (or databases) existing with local or regional entities (sectoral or local-based associations, e.g. ADL), the characterisation work should focus on aspects related to value chains for the main sectors installed in these territories, deepening knowledge about organisational, competency, market, technological and innovation dimensions. The methods to be mobilised are, information analysis and desk research, interviews and online surveys to representative samples in the universe of the 11 Portuguese BRs. | Companies, sector and local associations, producers, artisans and other entities based or active in the 11 BRs areas | QP | Edited Report | Nº | 1 | Diagnostic Report
18 | Identification of key actors in the socio-economic sector in the BR | 2021-01-01 | 2021-06-30 | The activity aims to identify the local players more qualified/predisposed to explore the opportunities for conservation and sustainable use of the resources in territories. To this end, contacts will be made with local or regional authorities (sectoral or local-based associations, e.g. ADL). The characterisation work should focus on the business and other locally based initiatives that are exploiting this opportunity or reveal the potential to do so. The methods to be used includes contacts, information analysis and desk research. | BR managers Local agents/players Local Community | IPN | Edited Report | Nº | 1 | Diagnostic Report
19 | Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development | 2021-01-01 | 2021-06-30 | The activity aims to identify best practices of R&TD, innovation and entrepreneurship aligned with sustainable development. It will be based on the diagnosis, capture and expansion of best practices in the territories of the region and international best practices, for integration into the strategy of each Portuguese Biosphere Reserves and for support in the work of local teams. The methods to be used includes contacts, literature review, information analysis and desk research. | BR managers Local agents/players Local Community SNTC (National Scientific and Technological System) Companies | IPN | Edited Report | Nº | 1 | Diagnostic Report
20 | Identification of priorities and projects in the areas of development and sustainability | 2021-05-01 | 2021-12-31 | In order to focus on what is really a priority in each of the 11 Portuguese BRs, the identification of priority development and sustainability areas will be carried out using the methodology of participation of the organisation of Focal Action Groups, following the methodology to be defined for Participatory Model, also involving the identification of ongoing or planned projects considered relevant, involving partnership with other BRs, national or international. | BR Managers/technicians Local agents/players Resident population/visitors Central Administration/Local Power ONG Scientific/school/artistic community General population | QP and other partners | Edited Report | Nº | 11 | Diagnostic Report
21 | Selection of key ES for the sustainable development of BR | 2021-02-01 | 2021-10-31 | Considering the identity aspects, objectives and priorities of each of the biosphere reserve, we will select which key ES, adjusted to the NCP concept, for the promotion of a sustainable development of endogenous natural resources in the BRs. This activity will use a participatory and collaborative multi-actor methodology, in which local actors (communities, owners, local entrepreneurs, managers) will identify which ecosystem products and services (following the concept of PCN) they consider priority in the BR where are inserted, using questionnaires, interviews and focus groups. This activity will be developed in partnership with the University of Bergen and the UNESCO Chair “Sustainable heritage and environmental management” of Norway, and will follow the methodology of participatory mapping and analysis of social and socio-ecological networks that have been successfully applied in BRs of Nordhordland, Norway. | BR Managers Local Owners and Communities | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | List of key ecosystem services for BRs | Nº | 11 | Activity Report
22 | Selection of indicators and development of methodology for assessing the condition / status of ES | 2021-04-01 | 2021-12-31 | The selection of indicators and development of the methodology for assessing the condition/status of ES, adjusted to the concept of NCP, will follow the analytical approach of the MAES defined for the European Union, including indicators derived from scientific knowledge, environmental legislation, political relevance, conservation status of habitats and species, soil and ocean quality and sustainable development, and which can be assessed for a reference year and in which changes can be detected over time. | BR Managers Local Owners and Communities | CFE-UC in conjunction with University of Bergen | List of indicators and Methodology for assessing the condition of ES | Nº | 1 | Activity Report
23 | ES condition / status assessment | 2021-07-01 | 2022-04-30 | The assessment of the state of ES will also follow the analytical approach of the MAES, and will use the indicators selected in the previous activity. | BR Managers Local Owners and Communities | CFE-UC in conjunction with University of Bergen | Determination of the quality of ES in each BR | Nº | 11 | Activity Report / Website
24 | ES valuation proposal (add value) | 2021-08-01 | 2022-07-31 | Survey of goods and services that currently bring benefits to the community and which can be valued in ecological, socio-cultural and economic terms, following a participatory methodology using surveys. | BR Managers Local Owners and Communities | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | List of valuable key ES and maps of valuation potential for each BR | Nº | 11 | Activity Report / Website
25 | ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action | 2021-08-01 | 2022-10-31 | Valuation of previously selected ES will be carried out using a combination of monetary and non-monetary approaches to develop estimates of economic, social and ecological values. The most adequate economic assessment method for each service will be selected, including market-based methods, travel costs and declared preference techniques. The results of the economic assessment and the ecological assessment will be used to provide an assessment of the value of the BRs ecosystems, based on stakeholders' perceptions and preferences towards ES. This activity will follow a participatory methodology, in which a selected group of stakeholders (scientists, BR managers and local players) will perform a holistic assessment of ES based on their assessment of ecological, economic and social value. These different dimensions of the value will be linked through a multi-criterion decision analysis structure. | Scientific Community BR mamagers ICNF Local Owners and Communities | CFE-UC | Determination of the economic and ecological value of the key ES of each BRs | Nº | 11 | Activity Report / Website
26 | Mapping BR ES | 2021-09-01 | 2022-10-31 | Data collected in previous tasks will be compiled into geodatabases. Using spatial interpolation techniques, the mapping of ES, following the NCP concept, will be carried out considering the three zones that make up de BRs. | BR managers ICNF Stakeholders Local Communities | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | Key ES maps of each BR | Nº | 11 | Activity Report / Website
27 | Proposal of management and conservation measures for BR and ES optimization" | 2021-11-01 | 2022-10-31 | Considering the identity aspects, objectives and priorities of each of the biosphere reserves, but also the condition/state of the ES, specific management and conservation measures will be proposed for each of the three BR zones, aiming at optimising the selected ES. | BR managers ICNF Stakeholders Local Communities | CFE-UC | List of ES management and conservation measures | Nº | 11 | Activity Report / Website
28 | ES modelling to assess the effectiveness of management and conservation measures | 2021-11-01 | 2022-10-31 | In this task, we will analyse and integrate all the results of the previous tasks using spatially explicit modelling using models already tested for different types of ES (e.g., INVEST, SOILNAVIGATOR, SolVES, AIRES) to evaluate the effectiveness of management and conservation measures proposed before their implementation, based on the collection of existing information on the potential that each ecosystem typology mapped to each BR has for the provision of ES, in the NCP approach, and how the proposed measures can evaluate and add value to endogenous natural resources. | Scientific Community BR Managers ICNF Stakeholders | CFE-UC in conjunction with University of Bergen | Maps resulting from the application of different modelled management and conservation measures | Nº | 33 | Activity Report / Website
29 | Use of key ES in mitigation and adaptation to climate change in BR - pilot action | 2022-05-01 | 2022-12-31 | Considering the identity aspects, objectives and priorities of each biosphere reserve, a key ES will be selected using a participatory and collaborative multi-player methodology, aiming at its role in mitigation and adaptation to climate change. The result of each of these pilot projects will be integrated into the SDPs of each BR. | Scientific Community BR Managers ICNF Stakeholders | CFE-UC in conjunction with University of Bergen | Edited Report | Nº | 11 | Pilot Actions Report
30 | ES Sustainable Management Manual for BR | 2022-09-01 | 2023-02-28 | Based on the modelling exercise and the results of the pilot projects, it is intended to create a manual for the sustainable management of ES and endogenous resources in BR (taking into account the specificities of each BR) including criteria for the selection and implementation of measures to promote and enhance ecosystems in the scope of the provision of ES and the methodologies for monitoring ES. | BR Managers Local Owners and Communities | CFE-UC | Manual on the sustainable management of ES and endogenous resources in BRs | Nº | 11 | Manual on the sustainable management of ES and endogenous resources in BRs
31 | Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR | 2022-03-01 | 2022-12-31 | Based on the diagnosis made, resulting from the set of activities of analysis, survey, characterisation, listening, involvement and participation of the entire project team, but also of stakeholders and general population, this activity aims to discuss strategic development options of each SDP, through public discussion sessions in each of the 11 BRs, betting on the development of SDPs that translate the realities of each BR and that are actually intended for each of the territories. | BR Managers/technicians Local agents/players Resident population/visitors Central Administration/Local Power ONG Scientific/school/artistic community General population | QP | Edited Report | Nº | 11 | Report of the SDPs Pre-Proposal
32 | SDP public presentations and discussions | 2022-09-01 | 2022-12-31 | The SDPs intended to develop will be associated with operational and management principles contained in national legislation, namely related to the right to participate, providing for the promotion of SDPs and the holding of public sessions to present them in order to encourage participation and obtaining contributions and suggestions for improvement. This will be carried out during the final stage of the project, which will be carried out in each of the 11 BRs. | General population | QP | Sessions held | Nº | 11 | Public Consultation Consideration Report
33 | Revision and editing of the final versions of the SDP | 2022-11-01 | 2023-03-31 | After the entire process of development of the SDPs of the BRs, the activity corresponds to the revision of the SDPs, given the contributions received in the Public Consultation and the follow-up and evaluation of the pilot action measures, and their edition. | BR Managers | QP | Edited Report | Nº | 11 | Sustainable Development Plan
34 | Selection of 11 pilot actions | 2021-04-01 | 2021-05-31 | Pilot actions will be selected through a collaborative process with BRs (managers and relevant actors), taking as reference the strategies and lines of action identified in the SDPs. Each BR will be involved in at least one pilot action and will be developed in such a way as to be easily transferred/replicated in any of the remaining BRs as well as other reserves in the world network of BR. A common methodology for follow-up/monitoring, evaluation and communication will be established for the different pilot actions. Delineated the “path” that is to be followed in each BR and stabilised the sustainable development proposal and its implementation programme/management, the selection of pilot actions to be implemented will involve the identification of a set of criteria to ensure that the measure to be developed is the best that adapts to each BR, which is achievable and can have continuity. | BR Managers | QP and other partners | Selected pilot actions | Nº | 11 | Pilot actions implemented
35 | Tourism "Script" for the Portuguese Biosphere Reserves - pilot action | 2021-06-01 | 2022-10-31 | The creation of tourist roadmaps results from the previous identification of elements of cultural heritage (tangible and intangible), natural heritage (biodiversity, landscape) carried out in the initial phase of the project, for each BR. The roadmaps will include elements and tourism activities such as gastronomy, wine tourism, local culture, historical-cultural and religious heritage, biodiversity, landscape, craftsmanship in conjunction with local players, whether companies or organisations as promoters of the itineraries. The roadmaps will include thematic activities such as walking tours, visits to monuments, festivities, Slow Tourism. Based on the roadmaps of each reserve, a National Roadmap of Portuguese Biosphere Reserves will be structured. The Roadmaps may constitute tehmselves as pilot actions. | BR Managers Communities and local partners Scientific Community | QP and other partners | Guidebooks made | Nº | 11 | Tourist Guidebooks
36 | Memories and identities - systematic record of memories | 2020-11-12 | 2021-09-30 | Local presentation of the project of recording memories to Reserves and Communities — awareness-raising and demonstration actions involving local partners. Invitation to collect and share testimonies and memories — involvement of local partners — including communication media; Organisation of actions of identification, collection (digital and in-person Memory Days in each Reserve), heritage status qualification and editing of interviews, oral and written testimonies, reproduction of objects and photographs - to be published in the portals associated with the program (Memory for All, websites of Reserves, eventual Reserves Memory Centres). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs according to activity. | BR Managers Communities and local partners | NOVA FCSH | Interviews held | Nº | 165 | Website
37 | Creation of memory and community spaces - pilot action | 2021-05-01 | 2023-05-11 | Promotion of collaborative and networked organisation of memory points/exhibitions involving Reserves and Communities in possible collaboration with local entities — including planning and training in the areas of educational services, programming; exchange programmes and, as far as possible, laboratory/hands-on dynamics associated with local realities, namely in the field of learning and valorisation of local practices and use of endogenous resources. This pilot action that can be replicated in other BRs that meet appropriate conditions and express this interest. | BR Managers Communities and local partners Local Authorities | NOVA FCSH | Memory centres created | Nº | 3 | Activity Report
38 | Network of Biosphere Reserves shops and virtual store - pilot action | 2021-10-01 | 2022-10-31 | The creation of a Network of Stores of Biosphere Reserves aims to promote the partnership between Biosphere Reserves in order to enhance value in the market of their endogenous and specific products (natural products, food, craftmanship, etc.) in a logic of strengthening the circular economy. In addition to promoting cooperation between producers of the same Reserve and between producers of the various Portuguese Reserves, the network of shops will allow links with other reserves at international level. Simultaneously, the project aims to contribute to the online distribution of these products, in a shared and collaborative way, favouring the positioning of small and micro producers in distribution and marketing. The project implies the development of the concept and model of exploitation of the store network, the concept of the store-type (physical spaces), layout and image, and the virtual store, associating itself with the branding proposals that will be made for the Portuguese Biosphere Reserves Network. | Local businesses and producers | QP | Virtual store created | Nº | 1 | Project website (Portuguese BR Network)
39 | Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks | 2022-01-01 | 2022-03-31 | The activity aims to identify the different systems of sustainable development indicators used in UNESCO's BR Network Reserves and the best practices implemented. It also includes the analysis of the indicators of the Portuguese Action Plan for BRs. It is intended to resort to the benchmarking process, also having the participation and experience of international partners and BRmanagers. | BR Managers/technicians | QP | Edited Report | Nº | 1 | SD Indicator System Report
40 | Architecture of SDP indicators and monitoring system | 2022-03-01 | 2022-07-31 | Identified the best group of indicators in practice, the design of the system of sustainable development indicators will be oriented to respond to the concerns already mentioned in the Application Notice, to be accessible to all and so that it can receive input regularly. In order to contribute to the improvement of environmental, economic, social and institutional performance management, the indicators to be included (execution and impact) will cover the different sectors and problems identified in the SDPs, enabling a practical monitoring plan to be established. | BR Managers National MAB Committee | QP and other partners | Edited Report | Nº | 1 | SD Indicator System Report
41 | Consultation and validation of the SDP indicators and monitoring system | 2022-07-01 | 2022-10-31 | After the structure, protocol, registration methodologies, treatment and systematisation of SDPs monitoring is established, with the identification of a robust set of sustainable development indicators, which will be submitted to the approval of the Advisory Committee, implementing the Participatory Model and promoting legitimacy of the process. The Monitoring Plans for each ofthe 11 BRs will be developed specifying in addition to the methodology to be observed in the collection of the data (locations and their frequency, techniques and equipment, evaluation criteria, etc.), the entities involved both in terms of availability information, either in terms of active participation in the collection and input to the plan. For this purpose, sheets shall be drawn up for each of the indicators systematising the requirements applicable to each indicator. | BR Managers National MAB Committee | QP and other partners | Edited Report | Nº | 1 | SD Indicator System Report
42 | Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System | 2022-09-01 | 2023-01-31 | This training contributes to the proper implementation of the Monitoring Plan of the BR network and associated Indicator System. Monitoring implies the definition of a scoreboard of indicators relevant to the network as a whole and for each reserve, of the methods and periodicity of collection, reporting and reporting. The training aims to train technicians associated with each BR to participate in this process throughout its cycle: definition, collection and availability. The concept and form of definition of indicators, the link between them and the reality to be monitored, the way to organise the collection and communication strategies (technical and generalist) are contents to be considered. The training will follow a practical approach in conjunction with the construction of the indicators system, working as an auxiliary resource for its implementation. The training will combine face-to-face and non-presential strategies ensuring broad and efficient participation of technicians associated with the management of reserves. | BR Managers Agents and institutions, public and private, operating in BR territories | QP and other partners | Persons covered in training | Nº | 50 | Report on the Training Execution and Certificates Issued
43 | Citizen Science for sustainable BR - pilot action | 2021-11-01 | 2022-05-30 | . Awareness-raising of the scientific community to participate in the validation and exploitation of data provided by citizen science activities and in the communication of results to the community. . Promoting and supporting citizen science initiatives — in conjunction with challenges raised to the scientific community, and in collaboration with the “Rede Portuguesa de Ciência Cidadã e Ciência Viva” (Portuguese Network of Citizen Science and Living Science). . Organisation of collaborative actions to mobilise communities and society in general for listening about topics for citizen science actions, identification and enrichment of content (availability of images for recognition, presentation of local activities and practices — crowdsourcing, hands-on actions - in addition to the usual work with the school community). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs | BR Managers Communities and local partners Scientific Community | NOVA FCSH | Citizen Science Initiatives held | Nº | 11 | Activity Report
44 | Creation of the sustainable development barometer for Portuguese Biosphere Reserves | 2022-10-01 | 2022-12-31 | The activity aims to promote sustainability in BR, fostering active participation of citizens, facilitating dialogue and the exchange of experiences and best practices, through the organisation of conferences, discussion platforms, among others, to explore new ways of addressing sustainable development issues. This activity includes the generation of reports and procedure of data publishing, both of monitoring results, as of communication and information actions, of execution and implementation of projects and of pilot actions and others, allowing constant follow-up and the sharing of knowledge, continuously and evolutionary, of the sustainable development process. | BR Managers/technicians International Partners | QP | Edited Report | Nº | 1 | Report of the Barometer for Sustainable Development of BRs
45 | Sustainability certification framework - Portuguese Biosphere Reserves | 2020-11-12 | 2023-04-11 | A certification and benchmark system will be created covering the activities, sectors, goods and services of BRs, based on principles of quality, best practices and valorisation of knowledge and local and traditional products. This benchmark will seek to promote the introduction of innovation, transparency, competitiveness and long-term business commitment. For the Tourism sector, as an example, the benchmark will be in line with the World Charter for Sustainable Tourism +20 (2015), the 2030 Agenda and the United Nations Sustainable Development Goals. The design of the system will be supported by a benchmarking analysis within the World BR Network. Awareness-raising and training actions will be organised in line with communication strategy, as well as the edition of Handbooks of Best Practice and a Guide to Sustainable Tourism in BRs. The Sustainable Tourism guide describes actions, products, services and players that promote Sustainable Tourism in BRs and will be aligned with the SDPs. | BR Managers Local agents: Companies, associations, producers, craftsmen Local Communities | QP and other partners | Benchmark and its regulatory framework | Nº | 1 | Normative Reference Report and Good Practice Manuals
46 | Assessment of training needs that will support the training planning | 2021-04-01 | 2021-10-31 | This activity aims to identify the skills needs of the management teams of Biosphere Reserves and local partner entities. This diagnosis will allow planning the training and capacitation activity to support the implementation of SDPs. The development of the SDPs will pose new challenges and demands for managers and technicians of the BR teams that, to be adequately answered, requiring the mobilisation of more and new skills. This activity presupposes a close link between the diagnostic strategy and the process of defining the main objectives and bets included in the SDPs, as well as a dynamic participation in consultation with BR teams, public decision-makers and experts to inform the diagnostic process. The diagnosis will allow to design plans specifically adapted to the contexts of professional practice of each of the BRs that will integrate a Training Plan to be developed throughout different stages of development of the project. | BR Managers Agents and institutions, public and private, operating in BR territories | QP and other partners | Edited Report | Nº | 1 | Diagnostic Report
47 | Governance skills reinforcement program for BR managers, partners and local agents | 2021-10-01 | 2022-10-31 | Responsibility for managing Biosphere Reserves is very demanding in terms of management skills. This requirement is increasing and requires a progressive greater professionalism of the management job. The objectives of strengthening its leading role associated with the implementation of the project developed here will contribute to recall and accelerate these needs. Thus, it is important to enable managers with management skills that allows them to respond positively to the greater complexity of the functions that they must assume and at the level of governance of the Reserves. The reference of these training priorities will also receive input from the diagnostic exercise of training needs that is part of the project's list of activities. Management skills and skills in the use of technological tools to support management will be priority areas of this formative approach. | BR Managers | QP and other partners | Persons covered in training | Nº | 25 | Report on the Training Execution and Certificates Issued
48 | Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP | 2021-05-01 | 2022-10-31 | This activity includes the implementation of the Training Plan developed in the context of the Diagnostic of Training Needs. The training programme to be developed will give priority to the areas of sustainable development (in conjunction with the implementation of the SDPs), cooperation, but also the collaborative approach that is important to ensure in the development of the project. This activity covers the training of BR management teams in nuclear fields for the proper implementation of SDPs and which will be referred to in the diagnostic exercise of training needs. Areas anticipated to be considered: management support skills (including technological tools); fundraising, project management, and transversal competencies — associated with collaboration, conflict negotiation and autonomy, proficiency in foreign languages, as well as collaborative work methodologies that structure the entire intervention strategy of the project. | BR Managers Agents and institutions, public and private, operating in BR territories | QP and other partners | Persons covered in training | Nº | 100 | Report on the Training Execution and Certificates Issued
49 | Training associated with the implementation of pilot actions | 2021-08-01 | 2022-10-31 | Identification and dissemination of new competences in models and more advantageous ways of sustainable management of resources with economic, social and cultural benefit for specific communities, for the type of pilot action and context in which they are carried out. | BR Managers | QP and other partners | Training actions | Nº | 11 | Presence sheets in the actions carried out
50 | Training of local teams to support economic initiatives and funding opportunities | 2022-01-01 | 2022-07-31 | The development of this activity involves the training of local BR teams, providing them with skills to support local innovation actions, carry out activities to support the economic initiative and contribute to the self-sustainability of their projects. Also includes support in the search for partnerships (companies and other stakeholders) and publica and private funding, for the new projects and for the Portuguese Biosphere Reserves (e.g. PT2030, Horizon Europe) Training topics: Innovation and technology transfer; Entrepreneurship and business opportunities, Funding opportunities. | BR Managers | IPN | Training actions | Nº | 1 | Number of persons covered in training
51 | Capacitation of local BR decision makers in implementing the Sustainable Management Plans | 2022-10-01 | 2023-03-31 | Holding digital training actions to train local decision-makers to implement sustainable management plans, about regarding to the ES proposed for each BR and development of a guide of best practices. | BR Managers/technicians | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | Digital training actions | Nº | 11 | Activity Report
52 | Technical workshop on ecosystem services | 2022-11-01 | 2023-05-11 | Holding technical workshops on ES, following the NCP concept, and monitoring methodologies in each BR. These workshops will include the participation of BRs from Norway (Nordhordland UNESCO Biosphere) and the University of Bergen, and the methodology for ES selection that this BR has been implementing with the participation of communities, as well as with the BRs of CPLP and Spain. | BR Managers/technicians | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | Workshops | Nº | 11 | Activity Report / Website
53 | Virtual incubation program in Portuguese Biosphere Reserves - pilot action | 2022-01-01 | 2022-06-30 | In this task, the IPN will implement a program to support the creation of businesses that explore the opportunities of BRs. The program will last 6 months, working continuously, where selected entrepreneurs will be able to explore the commercial validity of their project. As support, there will be workshops and mentoring with trainers and experts in the various areas. The methodology already tested in several accelerated programs where IPN, addresses the following topics: Ideation and Innovation, Business Model, Customer Development, Marketing for Entrepreneurs, Startups and Investment, Action Plan. | BR Managers Potential entrepreneurs | IPN | Training actions | Nº | 1 | Number of persons covered in training
54 | Program of visits and transfer of experiences between Portuguese BR and donor countries | 2021-09-30 | 2023-05-11 | The organisational themes of the short visit programme will be established on the basis of the priorities identified in the Sustainable Development Plans of Biosphere Reserves, pilot actions and other activities arising from the participation of Biosphere reserves in the cooperation networks of the MAB program. The involvement, as a formal partner, of the Nordhordland Biosphere Reserve, Norway, also implies the establishment of permanent contact between the Portuguese biosphere reserves and the only biosphere reserve in donor countries. As the UNESCO National Commission of Iceland is also a formal partner of this consortium, we consider the possibility of the Portuguese Biosphere reserves cooperating in the process of creating the first biosphere reserve in that country. | UBergen, RBNordhordland, CNU Islândia | QP and other partners | Visits held | Nº | 13 | Visits Report
55 | Final project seminar | 2022-12-01 | 2023-05-11 | The Seminar aims to present the results achieved by the project, in its various components, fostering networking and the exchange of best practices between agents and institutions related to BRs, in Portugal and in the world. It will be structured at different moments: plenary sessions with guests; communication panels, focused on the analysis of the results achieved by the project, involving elements of the project team and local stakeholders; round table discussions with participants in the Residency and Visiting Programs. Alongside this technical-scientific component, the Seminar will have an event of Promotion and Publishing of Good Practices in the Portuguese Biosphere Reserves that will include exhibition/exhibition areas and a public ceremony to reward projects, products and services that stand out for their innovative character; contribution to strengthening the cohesion and sustainability of the territory; and/or by the capacity to communicate and attract new audiences to the Portuguese BR. | MAB Committees National Commissions for UNESCO BR Managers Researchers and academics Agents and institutions, public and private, operating in BR territories General Public | QP and other partners | Seminar held | Nº | 1 | Holding of events Regulation edition
56 | Marketing Strategy Development | 2020-11-12 | 2020-12-31 | The development of a Marketing Strategy allows to create a coherent and consistent line of interaction between the projected value of each UNESCO Biosphere Reserve and the different target audience, starting from the characterisation of fundamental values on which supports the whole Communication Plan and its initiatives and activities. It aims to clearly identify which target audiences, which resources should be mobilised and a whole set of communication rules, either at the level of the different interface entities or between partners. It includes market analysis, local and national market study, trend and competition/peer analysis. Develops interconnection with the areas of Knowledge and Training. Defines the Mission, Vision and Value Proposition and Positioning of the project, in the framework of the themes of Territorial Marketing. Typifies the Audiences of all actions to be developed, establishes schedules and budgets for each set of activities. | BR Managers | PC&A | Edited Report | Nº | 1 | Strategy Report of Marketing
57 | Communication Plan Design | 2021-01-01 | 2021-02-28 | As a result of the Marketing Strategy, the Communication Plan covers the entire communicational scope of the brand, in an integrated way, formalising a communication strategy and the creativity associated with it. Its construction will be based on principles and rules that allow to project a growing awareness of local, national and international populations of the natural and cultural values that underpin the classification and distinction of each territory and its international integration into the Man & the Biosphere Programme and the UNESCO World Network of Biosphere Reserves. • Objectives of communication • Definition of communication ecosystem (touchpoints) • Axis of Communication • Typification of Personas and their journeys • Determination of the budget • Schedule for Actions | BR Managers | PC&A | Edited Report | Nº | 1 | Plan of Communication
58 | Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook) | 2021-03-01 | 2021-04-21 | The development of a brand Identity Strategy will define a set of rules to be complied with according to the tone and graphism defined for the brand, in order to ensure consistency in all pieces created. Creating a common identity based on a brand allows a wide dissemination and visibility of the territories of the Portuguese Biosphere Reserves, their promotion and their visiting. This includes the creation of a logo and its variants, brand signature, colour palette, among others. The final result will be reflected in a brand book that contains all the graphic guidelines of the brand to ensure its correct use. •Creation of the brand and badge (Logo) for the Sustainable Tourism Framework in Portuguese Biosphere Reserves •Corporate Identity •Logo and its versions of use •Brand book - Corporate Identity Manual •Brand Signature | BR Managers Local Communities Scientific Community | PC&A | Edited Report | Nº | 2 | Handbook of Corporate Identity
59 | Generic Creative Development | 2021-04-01 | 2021-06-30 | Creative Development includes the baseline design of the entire image definition of all creative pieces to be developed, both at the visual level and at the level of key messages used in all communication. It is crucial to ensure that the creative components are tailored to the specificity of each piece of communication, the medium (online/offline) and each target audience. In this way, each piece of communication must have its own creative rationale, not just a declension. The materialisation and production of the entire creative component is represented by the set of actions described in Chapter C (includes subsequent declension) • Creativity - basic concepts of corporate communication and campaign (s) • Guideline of strategic vectors • Adaptation of Corporate Identity to pieces of communication • Image design of different pieces of communication (Visual Mood, Communication Tone, Key visuals, etc..) | BR Managers | PC&A | Communication Parts | Nº | 25 | Final Arts
60 | Creative development of digital communication | 2021-04-01 | 2021-06-30 | The digital environment is essential to enhance communication to different target audiences in different areas and geographies and has very own characteristics. The Digital Communication Image Design should be defined according to the media and channels to be used in the digital sphere, according to the Communication Plan (either in the scope of information or publicity) • Digital Communication Strategy (definition of communication in social networks, website, etc...) • Generic creative design of the image applied to digital channels (website, etc...) | BR Managers Local Communities Scientific Community | PC&A | Communication Parts | Nº | 10 | Final Arts
61 | Productions and promotional materials - Offline | 2021-05-01 | 2021-08-31 | It includes all the declensions of the different pieces proposed for different formats and in the production of offline promotion Materials. The promotional materials will be produced in Portuguese, English and Spanish and adapted to each Biosphere Reserve, in addition to the general support for the promotion of World Network of Biosphere Reserves of UNESCO. Graphic application and contents unfolding for Print materials for subsequent production and/or printing of said materials and includes: • Registration and photographic survey of the 11 reserves • Book or thematic brochure on the Portuguese network of Biosphere Reserves (Portuguese and Spanish) • Handbook of good conduct for visitors with map and routes for discovery • Travelling exhibitions • Urban Signage in a radius surrounding the reserves + porticos w/logo • Maps with interpretative paths for each Reserve | BR Managers Local Communities Scientific Community | PC&A and other partners | Communication Parts | Nº | 14 | Manual; Book
62 | Productions and promotional materials - Oneline | 2021-05-01 | 2021-08-31 | Graphical and content application for digital channels for further creation and development of the same. • Website - (Web design and creation of start-up content (Portuguese and English) - beta and final version. Landing Pages • Interactive maps. • Guidebooks (in partnership with Turismo de Portugal) properly segmented and directed to different target audiences • Photo contest (s) with respective activation and competitions to be included in the digital plan in different channels • Management of Social Networks and Content | BR Managers Local Communities Scientific Community | PC&A and other partners | Communication Parts | Nº | 4 | Website, Maps, Guidebooks, Contests
63 | Productions and promotional materials - Audiovisual materials | 2021-08-01 | 2022-11-30 | • Promotional film about the MaB Program, its objectives and the identification of national Biosphere Reserves • Teasers extracted from promotional film for digital use • Documentaries about each of the Biosphere Reserves • Reportages • Radio SPOTs | BR Managers Local Communities Scientific Community | PC&A and other partners | Communication Parts | Nº | 20 | Documentaries; Reportages, Radio Spots
64 | Brand Activations | 2021-08-01 | 2023-05-11 | It includes the definition of the mechanics of each activation, the necessary materials and the contacts that must be made to ensure the action of the brand. • Biosphere Reserves Fair Activation in schools for environmental education within the scope of social responsibility • Participation in niche Tourism Fairs and design of “Fam trips” to promote reserves • Award in “Turismo Sustentável nas Reservas da Biosfera Portuguesas (Sustainable Tourism in Reserves of Portuguese Biosphere) to be awarded to agents/products/services that standout in the implementation of good practices in Sustainable Tourism in BRs • Thematic competitions on BRs (photography, films, short films and travelling exhibitions based on the materials produced • National Biosphere Olympiads | BR Managers Local Communities Scientific Community | PC&A and other partners | Communication Parts | Nº | 10 | Final Arts
65 | Public Relations | 2021-08-01 | 2023-05-11 | Promotion of activities related to the project in the media through content (interviews, reportages, news, etc.), making known the project and its Biosphere Reserves. The management of the media strategy includes the coordination of all actions developed in each of the specificities. | BR Managers Local Communities Scientific Community | PC&A and other partners | Disseminated activities | Nº | 300 | Contact log
66 | Media Strategy and Planning | 2021-08-01 | 2023-05-11 | The projection of the notoriety of each of the Biosphere Reserve requires a strong plan of means that should specify the sequence of the actions proposed in the duration of the project. In the purchase of media there will be peaks of communication, resulting from the type of exposure. | BR Managers Local Communities Scientific Community | PC&A and other partners | Edited Report | Nº | 1 | Media Strategy
67 | Media Strategy and Planning - Press | 2021-08-01 | 2023-02-28 | Definition of quantity of advertising inserts and duration of the campaign (s). | BR Managers Local Communities Scientific Community | PC&A and other partners | Edited Report | Nº | 1 | Report
68 | Media Strategy and Planning - Radio | 2021-08-01 | 2023-02-28 | Definition of campaign duration(s), SPOT duration, time of day, vehicles (radios, programmes), expected audience, budget management | BR Managers Local Communities Scientific Community | PC&A and other partners | Edited Report | Nº | 1 | Report
69 | Media Strategy and Planning - Digital | 2021-08-01 | 2023-02-28 | Definition of duration, format, vehicle, targeting, clicks and budget management. Examples, display and banner ads; rich media formats (pop-ups, video ads...); websites (e.g. partners, forums...); email; mobile; Search Engine Advertising (SEO, AdWords); Social Media. Includes management, metrics analysis and reporting. | BR Managers Local Communities Scientific Community | PC&A and other partners | Edited Report | Nº | 1 | Report
70 | Culture and Education Agenda | 2021-11-01 | 2022-10-31 | Mapping and Organisation of information related to the cultural and pedagogical offer of BRs. Updated mapping and characterisation: . of the resources and programs of each Reserve: documentation centres, structures and explanatory or similar activities, educational services, existing in each Reserve; . local and national partners — Schools, Living Science Centres, Libraries, Museums, Higher Education Institutions Organisation and production of content for portal, tourism, guidebooks] | BR Managers Resident population Tour operators Agents and cultural and artistic institutions and producers of the BRs International tourist market | NOVA FCSH | Online cultural agenda | Nº | 1 | Agenda available online
71 | Development of Awareness Plan for different audiences | 2021-01-01 | 2021-06-30 | The Awareness-raising Plan aims, in a complementary way with the Strategy and Communication Plan, to work with different target audience segments and in a manner appropriate to each of these parties, to raise awareness about the strategic role of the BRs in the framework of sustainable development, balanced and cohesive at national and international level. The different parties (population, players and agents, visitors) must become aware of the role that BRs should play, locally and globally, which implies deepening their knowledge, broadening their experience and intensifying their participation in the life of these territories. The development of this Plan implies the census of what local practices have been and aims to ensure coherence to the various activities that, during the project and in the future, make BR factors of well-being of populations and balance between Man and Nature. | BR Managers Communities and local partners Scientific Community General public | QP in conjunction with BR Managers | Edited Report | Nº | 1 | Awareness-raising Plan Report
72 | Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners | 2021-09-01 | 2021-12-31 | After the completion of the diagnostic phase/mapping of resources and the initiatives present in the territory of 11 BRs, it is proposed to hold sessions of presentation of the project, one in each of the BR. The objective will be to present the project, its objectives and activities plan, making an assessment of the work done so far, and sensitising them to the next stages of the work. Emphasis should be given to the planned training actions and pilot projects. ... These sessions also aim to raise awareness among local stakeholders on communication issues, challenging them to participate in the ongoing communication plan. | Managers of the 11 BRs Resident population Companies and institutions, both public and private, located/operating in the territories of BRs | QP and other partners | Sessions held | Nº | 11 | Presence sheets in the sessions held in each of the 11 BRs. Session clipping dossier
73 | ES awareness actions | 2022-11-01 | 2023-01-31 | These actions will be organised in each Biosphere Reserve, using focus groups and include communication about the “added value” associated with sustainable management of ES in BRs with exchange of experiences between players from different BRs. | BR Managers | CFE-UC | Sessions held | Nº | 11 | Presence sheets in the sessions held in each of the 11 BRs. Session clipping dossier
74 | Planning of the National Biosphere Olympics | 2021-02-01 | 2021-05-31 | In a first phase we will gather the Organising Committee and the Scientific Committee that will, respectively, plan the Olympiads and design the tests that the enrolled students will take. This planning will involve devising a regulation, a date plan for holding, number and type of tests, the location and logistics to carry-out the event, promoting and registration forms, the design of a website dedicated to the event, co-financed by potential sponsors, the type of prises/trophies to be awarded, launch and closing ceremonies, the formation of teams, etc. In planning the scientific part, the respective Commission will have to decide what topics and support materials are for students to prepare, what age levels are in competition, build the tests appropriate to those age levels, the criteria for evaluation and classification, the duration and size of the tests and how to deliver them. | Public and private schools of 1st, 2nd, 3rd cycles and secondary education | Ordem dos Biólogos | BR Olympiads held | Nº | 1 | Enrolment of pupils and schools
75 | Communication and dissemination of the BR Olympics | 2021-03-01 | 2021-08-31 | The BR Olympiads will be promoted through the website of the National Biology Olympiad and linked to the project's digital communication structure, with the information needed for schools to register and become aware of the tasks to be carried out. All the Schools Boards of the Country (including Autonomous Regions), all the Biology teachers listed in the Contact List of the Biology Olympiad or for having carried out training activities on the Training Centre of the Order of Biologists will also be contacted. Promotion will be made to other potential sponsors. The activity will be made with the knowledge and support of the Ministry of Education, through the directorate of General Education that already supports the different Science Olympiads. Registrations will be online by professors, designated Responsible Teachers (RTs), who are responsible for disseminating the event to students, registrations and creating the conditions necessary for holding the tests. | Public and private schools of 1st, 2nd, 3rd cycles and secondary education Ministry of Education/DGE Biology Teachers Media | Ordem dos Biólogos | Entities/persons contacted | Nº | 1000 | Project Website: refer to the specific “area” of the Olympiad Registrations made
76 | BR Olympics | 2021-09-01 | 2022-07-31 | The tests will have two try-outs. The first of a more theoretical nature about the knowledge of the BRs, which will be held at the School itself and the second, with the selected students, which will be held outside the School, preferably in a space of one of the BRs and which will aim to carry out work for the promotion of BRs. The winners of the Olympiads will be known during an awards ceremony to which students and their family members, schoolteachers and principals, sponsors, mayors of schools and BRs targeted, and the media will be invited. The awarded works will be published by the media and through all the communication media of the Chamber of Biologists. | Students and teachers of public and private schools of 1st, 2nd, 3rd cycles and secondary education | Ordem dos Biólogos | Participating Students | Nº | 200 | Project Website: refer to specific “area” of the Olympiads Clipping Dossier of news about the event
77 | Design and organization of Biosphere Reserve Festivals | 2021-04-01 | 2022-09-30 | Launch of the concept of a network of festivals organised by the BRs of Portugal, in the mainland and Autonomous Regions, focusing on artistic and cultural activities, which, while promoting mutual knowledge and cooperation between the communities concerned, associates cultural and artistic expressions contemporary practices of interpretation and enjoyment of these “sustainability laboratories” by communities from other BRs outside Portugal and tourism segments that favour sustainable practices. Parallel to the artistic and cultural programming, BR product shows, thematic workshops, aimed at the agents involved in tourism and open to the local population, will also be promoted, that promote the natural, cultural and economic potential of theBRs and contribute to improve the self-esteem of populations. | Communities resident in BRs, Portuguese and foreign Agents and cultural and artistic institutions Tourists, particularly segments seeking sustainable tourism | QP and other partners | Events held | Nº | 3 | Report of the 1st edition of the Network of Arts and Culture Festivals of Portugal's Biosphere Reserves, with an event in the Azores, one in Madeira and one in the Mainland Event Clipping Dossier
78 | BioKeepers - Club of Friends and caregivers of BR | 2021-06-01 | 2022-05-30 | Dynamisation of collaborative dynamics of support and promotion of Reserves, through the creation of a network/club of Friends of Reserves — Bio Keepers — also seeking the development of community sense/identity sentiment for the group in BR Club format with potential for aggregation via portal/infrastructure (ID specific, share shares, news, activities). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs according to activity. | BR Managers Communities and local partners Schools | KEEP | “Members”/BioKeepers | Nº | 1100 | Activity Report
79 | Atlas of Portuguese Biosphere reserves | 2022-05-01 | 2023-03-31 | Interactive digital publication and publication in book (Portuguese and English versions) + didactic and juvenile versions. Historical review of the BRs and the socio-cultural context in which they are inscribed. Georeferenced information of the characteristics of the Reserve (species, resources, landscapes...) | BR Managers Tourism General public | NOVA FCSH and other partners | Publications | Nº | 2 | Portal and books
80 | Knowledge extension | 2020-11-12 | 2022-05-30 | Development of strategies to extend knowledge of BRs to schools, senior public, among others: - Surveying/diagnosis and international benchmarks - Discussion in the headquarters of the National MAB Committee involving all BRs - Preparation of an integrated strategy for the extension of knowledge - Availability/Publication - HR training actions of BRs and/or partner entities | BR Managers Communities and local partners Schools | KEEP | Training actions | Nº | 11 | Activity Report
81 | Itinerant exhibition | 2021-09-01 | 2023-05-11 | Travelling exhibition intended to be presented at 11 BRs and other places that request. The exhibition will have a digital version available on the portal and can be downloaded and printed in schools and in other entities upon request. The preparation of the contents will be ensured by the NOVA in partnership. The design, production and presentation and promotion actions assumed by the area of communication. | BR Managers Communities and local partners Scientific Community General public | NOVA FCSH | Exhibition held | Nº | 12 | Activity Report

## 09_Call#3_Schedule
ANNEX I PROJECT 09_CALL#3 Biosphere Reserves: Sustainable Territories, Resilient communities
c) Schedule
Program Area | Activity ID | Activity Description | Indicator | Promoter / Partner | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A1 | 1 | Collection, compilation and systematisation of bibliographic and cartographic information that led to the creation of the 11 Biosphere Reserves (BRs) in order to identify the objectives and specificities of the territories, providing a baseline framework for the Sustainable Development Plans (SDP). The collection will be carried out through direct contact with each of the management units of the BRs, using one of the tools defined in the Participatory Model and will provide data to the project databases. This activity includes a “thinking tank” integrating international participants that will follow-up the development of the project which will allow consultation and exchange of experiences with different realities of the World Network of Biosphere Reserves (WNBR), thus reinforcing the potential for cooperation between BRs in the different MAB networks. This group includes BR managers from Spain, Chile, São Tomé and Príncipe, Mozambique, Guinea-Bissau, Mexico, Cape Verde, among others. | Edited Report | QP and other partners | bar: 2020 11 to 2021 4
A1 | 2 | Compilation of all existing cartographic and bibliographic information about BRs, from its inception to the present. All information concerning the protected areas correspnding to the core and buffer zones of each BR will be compiled, including their sector plans. The aim of the activity is to learn what is done and to evaluate the importance of the implementation of the planned actions, as well as any constraints, for the local community and BR managers. This activity is complementary to Activity 1 and should be linked with actions, after listening to managers, local agents and the local community, among others. The activity will provide data to the project databases. This activity includes local presentation of the project in BRs. | Edited Report | QP and other partners | bar: 2020 11 to 2021 4
A1 | 3 | The activity aims to analyse the geostrategic context in which each BRs fits into, in terms of thematic and geographical networks, national and international, and the analysis of its strategic reference framework, in particular the orientations and policies related to conservation and sustainability, and Programs in place with an impact on each BR. It will also be essential to identify the group of entities with jurisdiction in the different territories covered by BRs. | Edited Report | QP | bar: 2021 1 to 2021 3
A1 | 4 | Collection and organisation of content associated with the historical path and the process of affirmation and impact of each Reserve from local and national archives and libraries (e.g. Archive from RTP-RDP, Film library, Press, Documentation in each Reserve). Development and publication of a book on the history of the Reserves considering the various contexts evoked, among others, public and local policies for the environment, the importance, meaning and impact of the UNESCO classification. | Publications | NOVA FCSH and other partners | bar: 2020 11 to 2022 11
A1 | 5 | Definition of a data management plan that specifies the methodologies and parameters of creation, collection, storage, organisation, deposit, description, documentation and access to data for the whole project, following best practices, pursuing open access purposes and in strict compliance with the FAIR principles (Findable, Accessible, Interoperable, Reusable). The results of the work carried out, the information collected and the research carried out, which nature and content could allow, will be disseminated (where possible in open access) and preserved; knowledge about BRs should be expanded and shared with society in general; the data collected should be made available, making it possible to reuse them for scientific and cultural purposes. The plan will follow internationally defined standards and models, highlighting the use of the DMP online form Digital Curation Centre. | Availability of the Data Management Plan | NOVA FCSH and other partners | bar: 2020 11 to 2021 4
A1 | 6 | Listening about the perception, identification and characterisation of the cultural and natural vernacular heritage directed to the Reserves and local entities, through the construction and application of surveys in the initial phase of implementation of the project and in its final phase. | Surveys applied | NOVA FCSH and other partners | bar: 2020 11 to 2021 4
A1 | 7 | This activity is dedicated to the design of the SDPs development model, starting from a benchmarking analysis of existing SDPs in order to stabilise a structure, contents and methodologies for the SDPs of the 11 BRs, taking advantage of the best that is done in the UNESCO Biosphere Reserves Networks, allowing to innovate and focus the SDPs on the most pressing issues today (efficient use of resources, sustainable consumption, preservation of biodiversity and landscapes, mitigation and adaptation to climate change and other environmental, health risks, etc.). In addition to being related to Activity 54, betting on the exchange of experiences with partner countries in this application, the result of the activity will be approved under Activity 9. | SDPs consulted | QP and other partners | bar: 2021 3 to 2021 5
A1 | 8 | The activity is assumed as a strategic tool for the diagnosis and production of knowledge, for community development and for the training of the entities and population involved, among others. The methodology to be implemented will be linked with the guidelines established by the UNESCO MAB Program Strategy (2015-2025), the Lima Action Plan (2016-2025) and the Portuguese Action Plan for the Portuguese BRs network (2018-2025), with the existing and ongoing participatory activities in the BRs, but will be designed mainly focused on the expected results of the SDPs and will be cross-cuting to the 11 BRs. The National MAB Committee and the main local players will follow-up the creation of a specialised Focus Group, the development of surveys aimed at different target audiences, which will promote a program of meetings to discuss and follow-up the plans in each BR. The activity is linked with the remaining activities of characterisation and participatory involvement. | Developed methodology | QP and other partners | bar: 2021 5 to 2021 7
A1 | 9 | Once stabilised the methodological proposal of the SDPs (with the identification of the specificities of each SDP and organisation of development and participation mechanisms) and following a transparent and participatory process, it will be submitted for approval by the Advisory Committee, implementing the Participatory Model and promoting the legitimacy of the process. | Assent | QP | bar: 2021 8 to 2021 9
A1 | 10 | Creation of the systems architecture and respective functioning and governance model - distributed type - of digital infrastructure associated with biosphere reserves, comprising the following elements: A. BRs network presentation and information portal - internal and external promotion B. dashboard - graphical interface providing quick views of relevant key performance indicators (KPIs) - namely resulting from sustainability plans C. data infrastructure - integration of content databases and linkage with other infrastructures (e.g. GBIF, PRISC) | Edited Report | NOVA FCSH and other partners | bar: 2021 1 to 2021 6
A1 | 11 | Creation of website for presentation, enhancement and promotion of biosphere reserves as a whole - beta version in month 6 and final version on the deadline. It will aggregate the detailed information and the services provided by the reserves in its various domains: historical and heritage characterisation; ecosystem services; online stores of Biosphere Reserves; guidebooks and cultural and scientific paths in virtual format, with georeferencing; network of friends of Reserves - Biokeepers. It will also gather the information and make available the contents produced within the scope of the project. Includes programming and development of website/digital platform with custom applicational logic (database integration; webshop; APIs for integration with external services/entities), including front-end and back-end programming; testing; support and maintenance. | Website Launch | NOVA FCSH and other partners | bar: 2020 11 to 2023 5
A1 | 12 | Adoption of a Business Intelligence (BI) tool that allows to gather, produce and explore automatically indicators that support integrated management and decision making for all biosphere reserves. A collection of indicators (via a dashboard) will be made publicly available, which will allow the follow-up, integrated monitoring and impact assessment of the sustainable development model implemented. It links with measures relating to the conception of the system of indicators for sustainable development. | Availability of dashboard indicators | NOVA FCSH and other partners | bar: 2020 11 to 2023 5
A1 | 13 | Creation of a catalogue aggregating the set of existing research data on biosphere reserves, facilitating access to consolidated and existing information in other repositories and data sources. It will be developed in conjunction with the existing scientific research infrastructures in Portugal and other relevant entities/holders of content of this nature. | Created online catalogue | NOVA FCSH and other partners | bar: 2021 5 to 2023 5
A1 | 14 | Mapping and characterisation of the cultural and natural heritage associated with each Reserve and research development with archives, libraries, other local and national resources (documentation, objects, photographs and other collections). Organisation, treatment and production of content for promotion in the platforms and channels of the project, highlighting the creation of guidebooks of the natural heritage of BRs. The results of the activity in conjunction with the actions related to the preparation and development of the SDPs, as well as the preparation of Tourist Roadmaps for the Portuguese Biosphere Reserves. | Guidebooks made | NOVA FCSH | bar: 2020 11 to 2023 1
A1 | 15 | For each biosphere reserve, mapping of the existing ecosystems using geographic information systems and satellite images (Landsat and Sentinel) will be carried out. This approach will allow stratification of the three areas that constitute biosphere reserves and build Normalized difference vegetation indexes (NDVI), which will be used as proxies of the structural diversity of habitats and which in turn are proxies of biodiversity. | Maps of composition of ecosystems/habitats | CFE-UC | bar: 2020 11 to 2021 4
A1 | 16 | Identification of the potential provision ES will be carried out following a spatial landscape scale approach in order to determine spatial patterns and the overlapping (“stacking” concept) of the multiple services and functions of ecosystems, assessing their diversity and spatial heterogeneity in the three zones that makes up each BR. The evaluation of the potential provision ES will follow the analytical structure of the MAES and CICES, adjusted to the IPBES “Nature's contribution to people (NCP)” concept and will focus on indicators identified as relevant to map the ES. Thus, this task will assess the potential of each of the biosphere reserves in the provision of biotic and non-biotic, regulatory, social and cultural products and services, as well as identify the potential for the provisioning of endogenous natural resources. | List of potential ecosystem services | CFE-UC in conjunction with University of Bergen | bar: 2020 12 to 2021 5
A1 | 17 | The activity aims to update the strategic diagnostic information on the economic system existing in Portuguese BRs (based or with significant activity in these spaces) and relevant to the formulation of sustainable development strategies, particularly, in the valorisation of specific resources and tourism. Starting from repertoires (or databases) existing with local or regional entities (sectoral or local-based associations, e.g. ADL), the characterisation work should focus on aspects related to value chains for the main sectors installed in these territories, deepening knowledge about organisational, competency, market, technological and innovation dimensions. The methods to be mobilised are, information analysis and desk research, interviews and online surveys to representative samples in the universe of the 11 Portuguese BRs. | Edited Report | QP | bar: 2021 1 to 2021 10
A1 | 18 | The activity aims to identify the local players more qualified/predisposed to explore the opportunities for conservation and sustainable use of the resources in territories. To this end, contacts will be made with local or regional authorities (sectoral or local-based associations, e.g. ADL). The characterisation work should focus on the business and other locally based initiatives that are exploiting this opportunity or reveal the potential to do so. The methods to be used includes contacts, information analysis and desk research. | Edited Report | IPN | bar: 2021 1 to 2021 6
A1 | 19 | The activity aims to identify best practices of R&TD, innovation and entrepreneurship aligned with sustainable development. It will be based on the diagnosis, capture and expansion of best practices in the territories of the region and international best practices, for integration into the strategy of each Portuguese Biosphere Reserves and for support in the work of local teams. The methods to be used includes contacts, literature review, information analysis and desk research. | Edited Report | IPN | bar: 2021 1 to 2021 6
A1 | 20 | In order to focus on what is really a priority in each of the 11 Portuguese BRs, the identification of priority development and sustainability areas will be carried out using the methodology of participation of the organisation of Focal Action Groups, following the methodology to be defined for Participatory Model, also involving the identification of ongoing or planned projects considered relevant, involving partnership with other BRs, national or international. | Edited Report | QP and other partners | bar: 2021 5 to 2021 12
A1 | 21 | Considering the identity aspects, objectives and priorities of each of the biosphere reserve, we will select which key ES, adjusted to the NCP concept, for the promotion of a sustainable development of endogenous natural resources in the BRs. This activity will use a participatory and collaborative multi-actor methodology, in which local actors (communities, owners, local entrepreneurs, managers) will identify which ecosystem products and services (following the concept of PCN) they consider priority in the BR where are inserted, using questionnaires, interviews and focus groups. This activity will be developed in partnership with the University of Bergen and the UNESCO Chair “Sustainable heritage and environmental management” of Norway, and will follow the methodology of participatory mapping and analysis of social and socio-ecological networks that have been successfully applied in BRs of Nordhordland, Norway. | List of key ecosystem services for BRs | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | bar: 2021 2 to 2021 10
A1 | 22 | The selection of indicators and development of the methodology for assessing the condition/status of ES, adjusted to the concept of NCP, will follow the analytical approach of the MAES defined for the European Union, including indicators derived from scientific knowledge, environmental legislation, political relevance, conservation status of habitats and species, soil and ocean quality and sustainable development, and which can be assessed for a reference year and in which changes can be detected over time. | List of indicators and Methodology for assessing the condition of ES | CFE-UC in conjunction with University of Bergen | bar: 2021 4 to 2021 12
A1 | 23 | The assessment of the state of ES will also follow the analytical approach of the MAES, and will use the indicators selected in the previous activity. | Determination of the quality of ES in each BR | CFE-UC in conjunction with University of Bergen | bar: 2021 7 to 2022 4
A1 | 24 | Survey of goods and services that currently bring benefits to the community and which can be valued in ecological, socio-cultural and economic terms, following a participatory methodology using surveys. | List of valuable key ES and maps of valuation potential for each BR | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | bar: 2021 8 to 2022 7
A1 | 25 | Valuation of previously selected ES will be carried out using a combination of monetary and non-monetary approaches to develop estimates of economic, social and ecological values. The most adequate economic assessment method for each service will be selected, including market-based methods, travel costs and declared preference techniques. The results of the economic assessment and the ecological assessment will be used to provide an assessment of the value of the BRs ecosystems, based on stakeholders' perceptions and preferences towards ES. This activity will follow a participatory methodology, in which a selected group of stakeholders (scientists, BR managers and local players) will perform a holistic assessment of ES based on their assessment of ecological, economic and social value. These different dimensions of the value will be linked through a multi-criterion decision analysis structure. | Determination of the economic and ecological value of the key ES of each BRs | CFE-UC | bar: 2021 8 to 2022 10
A1 | 26 | Data collected in previous tasks will be compiled into geodatabases. Using spatial interpolation techniques, the mapping of ES, following the NCP concept, will be carried out considering the three zones that make up de BRs. | Key ES maps of each BR | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | bar: 2021 9 to 2022 10
A1 | 27 | Considering the identity aspects, objectives and priorities of each of the biosphere reserves, but also the condition/state of the ES, specific management and conservation measures will be proposed for each of the three BR zones, aiming at optimising the selected ES. | List of ES management and conservation measures | CFE-UC | bar: 2021 11 to 2022 10
A1 | 28 | In this task, we will analyse and integrate all the results of the previous tasks using spatially explicit modelling using models already tested for different types of ES (e.g., INVEST, SOILNAVIGATOR, SolVES, AIRES) to evaluate the effectiveness of management and conservation measures proposed before their implementation, based on the collection of existing information on the potential that each ecosystem typology mapped to each BR has for the provision of ES, in the NCP approach, and how the proposed measures can evaluate and add value to endogenous natural resources. | Maps resulting from the application of different modelled management and conservation measures | CFE-UC in conjunction with University of Bergen | bar: 2021 11 to 2022 10
A1 | 29 | Considering the identity aspects, objectives and priorities of each biosphere reserve, a key ES will be selected using a participatory and collaborative multi-player methodology, aiming at its role in mitigation and adaptation to climate change. The result of each of these pilot projects will be integrated into the SDPs of each BR. | Edited Report | CFE-UC in conjunction with University of Bergen | bar: 2022 5 to 2022 12
A1 | 30 | Based on the modelling exercise and the results of the pilot projects, it is intended to create a manual for the sustainable management of ES and endogenous resources in BR (taking into account the specificities of each BR) including criteria for the selection and implementation of measures to promote and enhance ecosystems in the scope of the provision of ES and the methodologies for monitoring ES. | Manual on the sustainable management of ES and endogenous resources in BRs | CFE-UC | bar: 2022 9 to 2023 2
A1 | 31 | Based on the diagnosis made, resulting from the set of activities of analysis, survey, characterisation, listening, involvement and participation of the entire project team, but also of stakeholders and general population, this activity aims to discuss strategic development options of each SDP, through public discussion sessions in each of the 11 BRs, betting on the development of SDPs that translate the realities of each BR and that are actually intended for each of the territories. | Edited Report | QP | bar: 2022 3 to 2022 12
A1 | 32 | The SDPs intended to develop will be associated with operational and management principles contained in national legislation, namely related to the right to participate, providing for the promotion of SDPs and the holding of public sessions to present them in order to encourage participation and obtaining contributions and suggestions for improvement. This will be carried out during the final stage of the project, which will be carried out in each of the 11 BRs. | Sessions held | QP | bar: 2022 9 to 2022 12
A1 | 33 | After the entire process of development of the SDPs of the BRs, the activity corresponds to the revision of the SDPs, given the contributions received in the Public Consultation and the follow-up and evaluation of the pilot action measures, and their edition. | Edited Report | QP | bar: 2022 11 to 2023 3
A1 | 34 | Pilot actions will be selected through a collaborative process with BRs (managers and relevant actors), taking as reference the strategies and lines of action identified in the SDPs. Each BR will be involved in at least one pilot action and will be developed in such a way as to be easily transferred/replicated in any of the remaining BRs as well as other reserves in the world network of BR. A common methodology for follow-up/monitoring, evaluation and communication will be established for the different pilot actions. Delineated the “path” that is to be followed in each BR and stabilised the sustainable development proposal and its implementation programme/management, the selection of pilot actions to be implemented will involve the identification of a set of criteria to ensure that the measure to be developed is the best that adapts to each BR, which is achievable and can have continuity. | Selected pilot actions | QP and other partners | bar: 2021 4 to 2021 5
C1 | 35 | The creation of tourist roadmaps results from the previous identification of elements of cultural heritage (tangible and intangible), natural heritage (biodiversity, landscape) carried out in the initial phase of the project, for each BR. The roadmaps will include elements and tourism activities such as gastronomy, wine tourism, local culture, historical-cultural and religious heritage, biodiversity, landscape, craftsmanship in conjunction with local players, whether companies or organisations as promoters of the itineraries. The roadmaps will include thematic activities such as walking tours, visits to monuments, festivities, Slow Tourism. Based on the roadmaps of each reserve, a National Roadmap of Portuguese Biosphere Reserves will be structured. The Roadmaps may constitute tehmselves as pilot actions. | Guidebooks made | QP and other partners | bar: 2021 6 to 2022 10
A1 | 36 | Local presentation of the project of recording memories to Reserves and Communities — awareness-raising and demonstration actions involving local partners. Invitation to collect and share testimonies and memories — involvement of local partners — including communication media; Organisation of actions of identification, collection (digital and in-person Memory Days in each Reserve), heritage status qualification and editing of interviews, oral and written testimonies, reproduction of objects and photographs - to be published in the portals associated with the program (Memory for All, websites of Reserves, eventual Reserves Memory Centres). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs according to activity. | Interviews held | NOVA FCSH | bar: 2020 11 to 2021 9
C1 | 37 | Promotion of collaborative and networked organisation of memory points/exhibitions involving Reserves and Communities in possible collaboration with local entities — including planning and training in the areas of educational services, programming; exchange programmes and, as far as possible, laboratory/hands-on dynamics associated with local realities, namely in the field of learning and valorisation of local practices and use of endogenous resources. This pilot action that can be replicated in other BRs that meet appropriate conditions and express this interest. | Memory centres created | NOVA FCSH | bar: 2021 5 to 2023 5
B1 | 38 | The creation of a Network of Stores of Biosphere Reserves aims to promote the partnership between Biosphere Reserves in order to enhance value in the market of their endogenous and specific products (natural products, food, craftmanship, etc.) in a logic of strengthening the circular economy. In addition to promoting cooperation between producers of the same Reserve and between producers of the various Portuguese Reserves, the network of shops will allow links with other reserves at international level. Simultaneously, the project aims to contribute to the online distribution of these products, in a shared and collaborative way, favouring the positioning of small and micro producers in distribution and marketing. The project implies the development of the concept and model of exploitation of the store network, the concept of the store-type (physical spaces), layout and image, and the virtual store, associating itself with the branding proposals that will be made for the Portuguese Biosphere Reserves Network. | Virtual store created | QP | bar: 2021 10 to 2022 10
A2 | 39 | The activity aims to identify the different systems of sustainable development indicators used in UNESCO's BR Network Reserves and the best practices implemented. It also includes the analysis of the indicators of the Portuguese Action Plan for BRs. It is intended to resort to the benchmarking process, also having the participation and experience of international partners and BRmanagers. | Edited Report | QP | bar: 2022 1 to 2022 3
A2 | 40 | Identified the best group of indicators in practice, the design of the system of sustainable development indicators will be oriented to respond to the concerns already mentioned in the Application Notice, to be accessible to all and so that it can receive input regularly. In order to contribute to the improvement of environmental, economic, social and institutional performance management, the indicators to be included (execution and impact) will cover the different sectors and problems identified in the SDPs, enabling a practical monitoring plan to be established. | Edited Report | QP and other partners | bar: 2022 3 to 2022 7
A2 | 41 | After the structure, protocol, registration methodologies, treatment and systematisation of SDPs monitoring is established, with the identification of a robust set of sustainable development indicators, which will be submitted to the approval of the Advisory Committee, implementing the Participatory Model and promoting legitimacy of the process. The Monitoring Plans for each ofthe 11 BRs will be developed specifying in addition to the methodology to be observed in the collection of the data (locations and their frequency, techniques and equipment, evaluation criteria, etc.), the entities involved both in terms of availability information, either in terms of active participation in the collection and input to the plan. For this purpose, sheets shall be drawn up for each of the indicators systematising the requirements applicable to each indicator. | Edited Report | QP and other partners | bar: 2022 7 to 2022 10
B1 | 42 | This training contributes to the proper implementation of the Monitoring Plan of the BR network and associated Indicator System. Monitoring implies the definition of a scoreboard of indicators relevant to the network as a whole and for each reserve, of the methods and periodicity of collection, reporting and reporting. The training aims to train technicians associated with each BR to participate in this process throughout its cycle: definition, collection and availability. The concept and form of definition of indicators, the link between them and the reality to be monitored, the way to organise the collection and communication strategies (technical and generalist) are contents to be considered. The training will follow a practical approach in conjunction with the construction of the indicators system, working as an auxiliary resource for its implementation. The training will combine face-to-face and non-presential strategies ensuring broad and efficient participation of technicians associated with the management of reserves. | Persons covered in training | QP and other partners | bar: 2022 9 to 2023 1
C2 | 43 | . Awareness-raising of the scientific community to participate in the validation and exploitation of data provided by citizen science activities and in the communication of results to the community. . Promoting and supporting citizen science initiatives — in conjunction with challenges raised to the scientific community, and in collaboration with the “Rede Portuguesa de Ciência Cidadã e Ciência Viva” (Portuguese Network of Citizen Science and Living Science). . Organisation of collaborative actions to mobilise communities and society in general for listening about topics for citizen science actions, identification and enrichment of content (availability of images for recognition, presentation of local activities and practices — crowdsourcing, hands-on actions - in addition to the usual work with the school community). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs | Citizen Science Initiatives held | NOVA FCSH | bar: 2021 11 to 2022 5
A2 | 44 | The activity aims to promote sustainability in BR, fostering active participation of citizens, facilitating dialogue and the exchange of experiences and best practices, through the organisation of conferences, discussion platforms, among others, to explore new ways of addressing sustainable development issues. This activity includes the generation of reports and procedure of data publishing, both of monitoring results, as of communication and information actions, of execution and implementation of projects and of pilot actions and others, allowing constant follow-up and the sharing of knowledge, continuously and evolutionary, of the sustainable development process. | Edited Report | QP | bar: 2022 10 to 2022 12
B1 | 45 | A certification and benchmark system will be created covering the activities, sectors, goods and services of BRs, based on principles of quality, best practices and valorisation of knowledge and local and traditional products. This benchmark will seek to promote the introduction of innovation, transparency, competitiveness and long-term business commitment. For the Tourism sector, as an example, the benchmark will be in line with the World Charter for Sustainable Tourism +20 (2015), the 2030 Agenda and the United Nations Sustainable Development Goals. The design of the system will be supported by a benchmarking analysis within the World BR Network. Awareness-raising and training actions will be organised in line with communication strategy, as well as the edition of Handbooks of Best Practice and a Guide to Sustainable Tourism in BRs. The Sustainable Tourism guide describes actions, products, services and players that promote Sustainable Tourism in BRs and will be aligned with the SDPs. | Benchmark and its regulatory framework | QP and other partners | bar: 2020 11 to 2023 3
A1 | 46 | This activity aims to identify the skills needs of the management teams of Biosphere Reserves and local partner entities. This diagnosis will allow planning the training and capacitation activity to support the implementation of SDPs. The development of the SDPs will pose new challenges and demands for managers and technicians of the BR teams that, to be adequately answered, requiring the mobilisation of more and new skills. This activity presupposes a close link between the diagnostic strategy and the process of defining the main objectives and bets included in the SDPs, as well as a dynamic participation in consultation with BR teams, public decision-makers and experts to inform the diagnostic process. The diagnosis will allow to design plans specifically adapted to the contexts of professional practice of each of the BRs that will integrate a Training Plan to be developed throughout different stages of development of the project. | Edited Report | QP and other partners | bar: 2021 4 to 2021 10
B1 | 47 | Responsibility for managing Biosphere Reserves is very demanding in terms of management skills. This requirement is increasing and requires a progressive greater professionalism of the management job. The objectives of strengthening its leading role associated with the implementation of the project developed here will contribute to recall and accelerate these needs. Thus, it is important to enable managers with management skills that allows them to respond positively to the greater complexity of the functions that they must assume and at the level of governance of the Reserves. The reference of these training priorities will also receive input from the diagnostic exercise of training needs that is part of the project's list of activities. Management skills and skills in the use of technological tools to support management will be priority areas of this formative approach. | Persons covered in training | QP and other partners | bar: 2021 10 to 2022 10
B1 | 48 | This activity includes the implementation of the Training Plan developed in the context of the Diagnostic of Training Needs. The training programme to be developed will give priority to the areas of sustainable development (in conjunction with the implementation of the SDPs), cooperation, but also the collaborative approach that is important to ensure in the development of the project. This activity covers the training of BR management teams in nuclear fields for the proper implementation of SDPs and which will be referred to in the diagnostic exercise of training needs. Areas anticipated to be considered: management support skills (including technological tools); fundraising, project management, and transversal competencies — associated with collaboration, conflict negotiation and autonomy, proficiency in foreign languages, as well as collaborative work methodologies that structure the entire intervention strategy of the project. | Persons covered in training | QP and other partners | bar: 2021 5 to 2022 10
B1 | 49 | Identification and dissemination of new competences in models and more advantageous ways of sustainable management of resources with economic, social and cultural benefit for specific communities, for the type of pilot action and context in which they are carried out. | Training actions | QP and other partners | bar: 2021 8 to 2022 10
B1 | 50 | The development of this activity involves the training of local BR teams, providing them with skills to support local innovation actions, carry out activities to support the economic initiative and contribute to the self-sustainability of their projects. Also includes support in the search for partnerships (companies and other stakeholders) and publica and private funding, for the new projects and for the Portuguese Biosphere Reserves (e.g. PT2030, Horizon Europe) Training topics: Innovation and technology transfer; Entrepreneurship and business opportunities, Funding opportunities. | Training actions | IPN | bar: 2022 1 to 2022 7
B1 | 51 | Holding digital training actions to train local decision-makers to implement sustainable management plans, about regarding to the ES proposed for each BR and development of a guide of best practices. | Digital training actions | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | bar: 2022 10 to 2023 3
B1 | 52 | Holding technical workshops on ES, following the NCP concept, and monitoring methodologies in each BR. These workshops will include the participation of BRs from Norway (Nordhordland UNESCO Biosphere) and the University of Bergen, and the methodology for ES selection that this BR has been implementing with the participation of communities, as well as with the BRs of CPLP and Spain. | Workshops | CFE-UC in conjunction with University of Bergen and BR of Nordhordland | bar: 2022 11 to 2023 5
B1 | 53 | In this task, the IPN will implement a program to support the creation of businesses that explore the opportunities of BRs. The program will last 6 months, working continuously, where selected entrepreneurs will be able to explore the commercial validity of their project. As support, there will be workshops and mentoring with trainers and experts in the various areas. The methodology already tested in several accelerated programs where IPN, addresses the following topics: Ideation and Innovation, Business Model, Customer Development, Marketing for Entrepreneurs, Startups and Investment, Action Plan. | Training actions | IPN | bar: 2022 1 to 2022 6
B2 | 54 | The organisational themes of the short visit programme will be established on the basis of the priorities identified in the Sustainable Development Plans of Biosphere Reserves, pilot actions and other activities arising from the participation of Biosphere reserves in the cooperation networks of the MAB program. The involvement, as a formal partner, of the Nordhordland Biosphere Reserve, Norway, also implies the establishment of permanent contact between the Portuguese biosphere reserves and the only biosphere reserve in donor countries. As the UNESCO National Commission of Iceland is also a formal partner of this consortium, we consider the possibility of the Portuguese Biosphere reserves cooperating in the process of creating the first biosphere reserve in that country. | Visits held | QP and other partners | bar: 2021 9 to 2023 5
B2 | 55 | The Seminar aims to present the results achieved by the project, in its various components, fostering networking and the exchange of best practices between agents and institutions related to BRs, in Portugal and in the world. It will be structured at different moments: plenary sessions with guests; communication panels, focused on the analysis of the results achieved by the project, involving elements of the project team and local stakeholders; round table discussions with participants in the Residency and Visiting Programs. Alongside this technical-scientific component, the Seminar will have an event of Promotion and Publishing of Good Practices in the Portuguese Biosphere Reserves that will include exhibition/exhibition areas and a public ceremony to reward projects, products and services that stand out for their innovative character; contribution to strengthening the cohesion and sustainability of the territory; and/or by the capacity to communicate and attract new audiences to the Portuguese BR. | Seminar held | QP and other partners | bar: 2022 12 to 2023 5
C1 | 56 | The development of a Marketing Strategy allows to create a coherent and consistent line of interaction between the projected value of each UNESCO Biosphere Reserve and the different target audience, starting from the characterisation of fundamental values on which supports the whole Communication Plan and its initiatives and activities. It aims to clearly identify which target audiences, which resources should be mobilised and a whole set of communication rules, either at the level of the different interface entities or between partners. It includes market analysis, local and national market study, trend and competition/peer analysis. Develops interconnection with the areas of Knowledge and Training. Defines the Mission, Vision and Value Proposition and Positioning of the project, in the framework of the themes of Territorial Marketing. Typifies the Audiences of all actions to be developed, establishes schedules and budgets for each set of activities. | Edited Report | PC&A | bar: 2020 11 to 2020 12
C1 | 57 | As a result of the Marketing Strategy, the Communication Plan covers the entire communicational scope of the brand, in an integrated way, formalising a communication strategy and the creativity associated with it. Its construction will be based on principles and rules that allow to project a growing awareness of local, national and international populations of the natural and cultural values that underpin the classification and distinction of each territory and its international integration into the Man & the Biosphere Programme and the UNESCO World Network of Biosphere Reserves. • Objectives of communication • Definition of communication ecosystem (touchpoints) • Axis of Communication • Typification of Personas and their journeys • Determination of the budget • Schedule for Actions | Edited Report | PC&A | bar: 2021 1 to 2021 2
C1 | 58 | The development of a brand Identity Strategy will define a set of rules to be complied with according to the tone and graphism defined for the brand, in order to ensure consistency in all pieces created. Creating a common identity based on a brand allows a wide dissemination and visibility of the territories of the Portuguese Biosphere Reserves, their promotion and their visiting. This includes the creation of a logo and its variants, brand signature, colour palette, among others. The final result will be reflected in a brand book that contains all the graphic guidelines of the brand to ensure its correct use. •Creation of the brand and badge (Logo) for the Sustainable Tourism Framework in Portuguese Biosphere Reserves •Corporate Identity •Logo and its versions of use •Brand book - Corporate Identity Manual •Brand Signature | Edited Report | PC&A | bar: 2021 3 to 2021 4
C1 | 59 | Creative Development includes the baseline design of the entire image definition of all creative pieces to be developed, both at the visual level and at the level of key messages used in all communication. It is crucial to ensure that the creative components are tailored to the specificity of each piece of communication, the medium (online/offline) and each target audience. In this way, each piece of communication must have its own creative rationale, not just a declension. The materialisation and production of the entire creative component is represented by the set of actions described in Chapter C (includes subsequent declension) • Creativity - basic concepts of corporate communication and campaign (s) • Guideline of strategic vectors • Adaptation of Corporate Identity to pieces of communication • Image design of different pieces of communication (Visual Mood, Communication Tone, Key visuals, etc..) | Communication Parts | PC&A | bar: 2021 4 to 2021 6
C1 | 60 | The digital environment is essential to enhance communication to different target audiences in different areas and geographies and has very own characteristics. The Digital Communication Image Design should be defined according to the media and channels to be used in the digital sphere, according to the Communication Plan (either in the scope of information or publicity) • Digital Communication Strategy (definition of communication in social networks, website, etc...) • Generic creative design of the image applied to digital channels (website, etc...) | Communication Parts | PC&A | bar: 2021 4 to 2021 6
C1 | 61 | It includes all the declensions of the different pieces proposed for different formats and in the production of offline promotion Materials. The promotional materials will be produced in Portuguese, English and Spanish and adapted to each Biosphere Reserve, in addition to the general support for the promotion of World Network of Biosphere Reserves of UNESCO. Graphic application and contents unfolding for Print materials for subsequent production and/or printing of said materials and includes: • Registration and photographic survey of the 11 reserves • Book or thematic brochure on the Portuguese network of Biosphere Reserves (Portuguese and Spanish) • Handbook of good conduct for visitors with map and routes for discovery • Travelling exhibitions • Urban Signage in a radius surrounding the reserves + porticos w/logo • Maps with interpretative paths for each Reserve | Communication Parts | PC&A and other partners | bar: 2021 5 to 2021 8
C1 | 62 | Graphical and content application for digital channels for further creation and development of the same. • Website - (Web design and creation of start-up content (Portuguese and English) - beta and final version. Landing Pages • Interactive maps. • Guidebooks (in partnership with Turismo de Portugal) properly segmented and directed to different target audiences • Photo contest (s) with respective activation and competitions to be included in the digital plan in different channels • Management of Social Networks and Content | Communication Parts | PC&A and other partners | bar: 2021 5 to 2021 8
C1 | 63 | • Promotional film about the MaB Program, its objectives and the identification of national Biosphere Reserves • Teasers extracted from promotional film for digital use • Documentaries about each of the Biosphere Reserves • Reportages • Radio SPOTs | Communication Parts | PC&A and other partners | bar: 2021 8 to 2022 11
C1 | 64 | It includes the definition of the mechanics of each activation, the necessary materials and the contacts that must be made to ensure the action of the brand. • Biosphere Reserves Fair Activation in schools for environmental education within the scope of social responsibility • Participation in niche Tourism Fairs and design of “Fam trips” to promote reserves • Award in “Turismo Sustentável nas Reservas da Biosfera Portuguesas (Sustainable Tourism in Reserves of Portuguese Biosphere) to be awarded to agents/products/services that standout in the implementation of good practices in Sustainable Tourism in BRs • Thematic competitions on BRs (photography, films, short films and travelling exhibitions based on the materials produced • National Biosphere Olympiads | Communication Parts | PC&A and other partners | bar: 2021 8 to 2023 5
C1 | 65 | Promotion of activities related to the project in the media through content (interviews, reportages, news, etc.), making known the project and its Biosphere Reserves. The management of the media strategy includes the coordination of all actions developed in each of the specificities. | Disseminated activities | PC&A and other partners | bar: 2021 8 to 2023 5
C1 | 66 | The projection of the notoriety of each of the Biosphere Reserve requires a strong plan of means that should specify the sequence of the actions proposed in the duration of the project. In the purchase of media there will be peaks of communication, resulting from the type of exposure. | Edited Report | PC&A and other partners | bar: 2021 8 to 2023 5
C1 | 67 | Definition of quantity of advertising inserts and duration of the campaign (s). | Edited Report | PC&A and other partners | bar: 2021 8 to 2023 2
C1 | 68 | Definition of campaign duration(s), SPOT duration, time of day, vehicles (radios, programmes), expected audience, budget management | Edited Report | PC&A and other partners | bar: 2021 8 to 2023 2
C1 | 69 | Definition of duration, format, vehicle, targeting, clicks and budget management. Examples, display and banner ads; rich media formats (pop-ups, video ads...); websites (e.g. partners, forums...); email; mobile; Search Engine Advertising (SEO, AdWords); Social Media. Includes management, metrics analysis and reporting. | Edited Report | PC&A and other partners | bar: 2021 8 to 2023 2
C1 | 70 | Mapping and Organisation of information related to the cultural and pedagogical offer of BRs. Updated mapping and characterisation: . of the resources and programs of each Reserve: documentation centres, structures and explanatory or similar activities, educational services, existing in each Reserve; . local and national partners — Schools, Living Science Centres, Libraries, Museums, Higher Education Institutions Organisation and production of content for portal, tourism, guidebooks] | Online cultural agenda | NOVA FCSH | bar: 2021 11 to 2022 10
C2 | 71 | The Awareness-raising Plan aims, in a complementary way with the Strategy and Communication Plan, to work with different target audience segments and in a manner appropriate to each of these parties, to raise awareness about the strategic role of the BRs in the framework of sustainable development, balanced and cohesive at national and international level. The different parties (population, players and agents, visitors) must become aware of the role that BRs should play, locally and globally, which implies deepening their knowledge, broadening their experience and intensifying their participation in the life of these territories. The development of this Plan implies the census of what local practices have been and aims to ensure coherence to the various activities that, during the project and in the future, make BR factors of well-being of populations and balance between Man and Nature. | Edited Report | QP in conjunction with BR Managers | bar: 2021 1 to 2021 6
C2 | 72 | After the completion of the diagnostic phase/mapping of resources and the initiatives present in the territory of 11 BRs, it is proposed to hold sessions of presentation of the project, one in each of the BR. The objective will be to present the project, its objectives and activities plan, making an assessment of the work done so far, and sensitising them to the next stages of the work. Emphasis should be given to the planned training actions and pilot projects. ... These sessions also aim to raise awareness among local stakeholders on communication issues, challenging them to participate in the ongoing communication plan. | Sessions held | QP and other partners | bar: 2021 9 to 2021 12
C2 | 73 | These actions will be organised in each Biosphere Reserve, using focus groups and include communication about the “added value” associated with sustainable management of ES in BRs with exchange of experiences between players from different BRs. | Sessions held | CFE-UC | bar: 2022 11 to 2023 1
C2 | 74 | In a first phase we will gather the Organising Committee and the Scientific Committee that will, respectively, plan the Olympiads and design the tests that the enrolled students will take. This planning will involve devising a regulation, a date plan for holding, number and type of tests, the location and logistics to carry-out the event, promoting and registration forms, the design of a website dedicated to the event, co-financed by potential sponsors, the type of prises/trophies to be awarded, launch and closing ceremonies, the formation of teams, etc. In planning the scientific part, the respective Commission will have to decide what topics and support materials are for students to prepare, what age levels are in competition, build the tests appropriate to those age levels, the criteria for evaluation and classification, the duration and size of the tests and how to deliver them. | BR Olympiads held | Ordem dos Biólogos | bar: 2021 2 to 2021 5
C2 | 75 | The BR Olympiads will be promoted through the website of the National Biology Olympiad and linked to the project's digital communication structure, with the information needed for schools to register and become aware of the tasks to be carried out. All the Schools Boards of the Country (including Autonomous Regions), all the Biology teachers listed in the Contact List of the Biology Olympiad or for having carried out training activities on the Training Centre of the Order of Biologists will also be contacted. Promotion will be made to other potential sponsors. The activity will be made with the knowledge and support of the Ministry of Education, through the directorate of General Education that already supports the different Science Olympiads. Registrations will be online by professors, designated Responsible Teachers (RTs), who are responsible for disseminating the event to students, registrations and creating the conditions necessary for holding the tests. | Entities/persons contacted | Ordem dos Biólogos | bar: 2021 3 to 2021 8
C2 | 76 | The tests will have two try-outs. The first of a more theoretical nature about the knowledge of the BRs, which will be held at the School itself and the second, with the selected students, which will be held outside the School, preferably in a space of one of the BRs and which will aim to carry out work for the promotion of BRs. The winners of the Olympiads will be known during an awards ceremony to which students and their family members, schoolteachers and principals, sponsors, mayors of schools and BRs targeted, and the media will be invited. The awarded works will be published by the media and through all the communication media of the Chamber of Biologists. | Participating Students | Ordem dos Biólogos | bar: 2021 9 to 2022 7
C2 | 77 | Launch of the concept of a network of festivals organised by the BRs of Portugal, in the mainland and Autonomous Regions, focusing on artistic and cultural activities, which, while promoting mutual knowledge and cooperation between the communities concerned, associates cultural and artistic expressions contemporary practices of interpretation and enjoyment of these “sustainability laboratories” by communities from other BRs outside Portugal and tourism segments that favour sustainable practices. Parallel to the artistic and cultural programming, BR product shows, thematic workshops, aimed at the agents involved in tourism and open to the local population, will also be promoted, that promote the natural, cultural and economic potential of theBRs and contribute to improve the self-esteem of populations. | Events held | QP and other partners | bar: 2021 4 to 2022 9
C2 | 78 | Dynamisation of collaborative dynamics of support and promotion of Reserves, through the creation of a network/club of Friends of Reserves — Bio Keepers — also seeking the development of community sense/identity sentiment for the group in BR Club format with potential for aggregation via portal/infrastructure (ID specific, share shares, news, activities). The activity will take place in all BRs and is part of the catalogue of projects that can be selected by BRs according to activity. | “Members”/BioKeepers | KEEP | bar: 2021 6 to 2022 5
C1 | 79 | Interactive digital publication and publication in book (Portuguese and English versions) + didactic and juvenile versions. Historical review of the BRs and the socio-cultural context in which they are inscribed. Georeferenced information of the characteristics of the Reserve (species, resources, landscapes...) | Publications | NOVA FCSH and other partners | bar: 2022 5 to 2023 3
B1 | 80 | Development of strategies to extend knowledge of BRs to schools, senior public, among others: - Surveying/diagnosis and international benchmarks - Discussion in the headquarters of the National MAB Committee involving all BRs - Preparation of an integrated strategy for the extension of knowledge - Availability/Publication - HR training actions of BRs and/or partner entities | Training actions | KEEP | bar: 2020 11 to 2022 5
C1 | 81 | Travelling exhibition intended to be presented at 11 BRs and other places that request. The exhibition will have a digital version available on the portal and can be downloaded and printed in schools and in other entities upon request. The preparation of the contents will be ensured by the NOVA in partnership. The design, production and presentation and promotion actions assumed by the area of communication. | Exhibition held | NOVA FCSH | bar: 2021 9 to 2023 5

## 09_Call#3_Budget (Rev.01)
ANNEX I PROJECT 09_CALL#3 Biosphere Reserves: Sustainable Territories, Resilient communities
d) Budget
Programme: | Environment, Climate Change and Low Carbon Economy Programme
Project title: | Biosphere Reserves: sustainable territories, resilient communities
Project Promoter: | Quaternaire Portugal, SA
Total project cost: | 2198666.46
Project grant rate: | 100%
Project duration: | 30 months
| Unit | Number of units (a) | Unit price (€) (b) | Total cost (€) (a) x (b) | Type of expenditure | Comments/ Additional information | Guidance** | Project Promoter / Partner
1. DIRECT EXPENDITURES*
Management cost
Technical-scientific coordination of the project | months | 30 | 4735.73 | 142071.9 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 70% of the time |  | Quaternaire Portugal, SA
Executive coordination of the project | months | 30 | 1237.5 | 37125 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 24% of the time |  | Quaternaire Portugal, SA
Support for executive coordination | months | 30 | 1712.16 | 51364.8 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 42% of the time |  | Quaternaire Portugal, SA
Management and administrative team assigned to the project | months | 30 | 1505.08 | 45152.4 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of one element at 17%, other at 40% and another at 5% of the time |  | Quaternaire Portugal, SA
Provision of analytical accounting services within the scope of the project | months | 30 | 216.462 | 6493.86 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Service Agreement contract (fees and license fee for the analytical accounting software) |  | Quaternaire Portugal, SA
Trips of project coordination, management and administrative teams | trip | 36 | 150 | 5400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs of the coordination, management and administrative teams on the mainland |  | Quaternaire Portugal, SA
Trips of project coordination | trip | 17 | 400 | 6800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Costs of trips of the coordination and management teams to the islands |  | Quaternaire Portugal, SA
Trips for project coordination, management and administrative teams - cost-of-living allowance | days | 150 | 69.19 | 10378.5 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Use of computer equipment by the administrative team | months | 30 | 96.75 | 2902.5 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
Acquisition of new IT equipment for the coordination team | computer | 3 | 1650 | 4950 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | Acquisition of 2 laptops and 1 fixed computer with its accessories. |  | Quaternaire Portugal, SA
Management work platform for use with partners | months | 30 | 46.04 | 1381.2 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Costs of a Google Workspace Business |  | Quaternaire Portugal, SA
Statutory auditor's fees | months | 30 | 80 | 2400 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | Services provided by the statutory auditor |  | Quaternaire Portugal, SA
Financial costs related to the project bank account | year | 2.5 | 128 | 320 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | Maintenance fees and transfer charges for Partners |  | Quaternaire Portugal, SA
Total 1.1: |  |  |  | 316740.16
Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR)
Search and development of the list of information to be collected | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Valor médio /homem / dia para uma equipa de quadros superiores que integra Administrador, Consultor-coordenador e consultor / Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Draw up of requests for information, through direct contact with each of the BRmanagers | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of the information received | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Loading into the project database | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 28 | 2 | 56 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.2: |  |  |  | 4736
Output / Activity 2 - Survey of existing BR action plans, objectives and priorities.
Summary of the various management documents existing in the BRs (action plans, management reports, etc.) identifying, namely, priorities and projects in progress or planned to be validated | days | 47 | 180 | 8460 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Fieldwork and meetings with BR managers on the mainland | trip | 0 | 0 | 0 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Fieldwork and Meetings with BR managers in the Islands | trip | 0 | 0 | 0 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 0 | 0 | 0 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Updating the objectives and priority projects of each BR | days | 30 | 180 | 5400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Utilização de equipamentos informáticos/ Use of computer equipment | days | 55 | 2 | 110 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.3: |  |  |  | 13970
Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks
Identification of the Strategic Reference Framework | days | 7 | 200 | 1400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of information | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of the objectives, indicators and goals of the different documents with an impact on PR | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of critical aspects | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of the governance framework | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Formalisation of the Geostrategic Framework Report | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 44 | 2 | 88 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
Total 1.4: |  |  |  | 8088
Output / Activity 4 - History of BR
Production and revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); historical and heritage research; preparation, production and editing of contents |  | Universidade Nova de Lisboa
Database | numeric | 1 | 6150 | 6150 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for database development |  | Universidade Nova de Lisboa
Research Trips | days | 5 | 1580 | 7900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips of research scholarship holders (data collection) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
Total 1.5: |  |  |  | 27308
Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the data management plan |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.6: |  |  |  | 2392
Output / Activity 6 - Auscultation / Perception and identification of heritage
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); data/information survey |  | Universidade Nova de Lisboa
Research Trips | days | 6 | 1580 | 9480 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip of research scholarship holder (data survey) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.7: |  |  |  | 11872
Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR
Benchmarking analysis of existing international and national SDPs | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Contact with international partners | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Identification of frameworks, contents and typologies of proposals, development methodologies, ways of participation and follow-up, management and execution model | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Selection of best practices | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Integration of critical aspects of the SRF (Strategic Reference Framework) | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Design of the structure, contents and methodologies for SDPs | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Formalisation of the Report Structure of the SDPs to be submitted for approval (Activity 9) | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Review and edition of the final version of the SDPs Structure Report (after approval - Activity 9) | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 42 | 2 | 84 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.8: |  |  |  | 8124
Output / Activity 8 - Development of the participatory planning methodology for the SDP
Identification of the practices and guidelines established in the Lima Plan | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of entities, agents, experts and others to be involved | days | 3 | 200 | 600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Cross-check with Activity 7 results to identify the best practices already being applied | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of weaknesses | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Proposals for new participatory practices | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Establishment of the Supervising Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Establishment of the approach methodology | days | 5 | 200 | 1000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Programming of the different participation periods and their associated methods | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the Participatory Planning Methodology Report | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 31 | 2 | 62 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
Total 1.9: |  |  |  | 5842
Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP
Organisation of the presentation session of the SDPs Structure Report | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Presentation of the SDPs Structure Report to the Supervisor Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of contributions received | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 10 | 2 | 20 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.10: |  |  |  | 1860
Output / Activity 10 - Digital Infrastructure - distributed management model
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the digital infrastructure management model |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.11: |  |  |  | 2392
Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website
Website development and programming | numeric | 1 | 64575 | 64575 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for development and programming of website/digital platform of the Biosphere Reserves with custom application logic (integration with databases; virtual store; APIs for integration with services/external entities) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.12: |  |  |  | 64575
Output / Activity 12 - Digital infrastructure - Indicators management dashboard
Business Intelligence Platform | numeric | 1 | 24600 | 24600 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for business intelligence platform development |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.13: |  |  |  | 24600
Output / Activity 13 - Digital Infrastructure - Research Data Catalog
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the data catalogue |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.14: |  |  |  | 2392
Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); preparation and production of content based on the historical research developed |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.15: |  |  |  | 13258
Output / Activity 15 - Mapping the BR ecosystem diversity
Computer equipment - high performance desktop computer | computer | 1 | 2136 | 2136 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €3,000, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Computer equipment - high performance desktop computer | laptop | 1 | 1780 | 1780 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €2,500, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Computer equipment - External storage disks | disk | 4 | 178 | 712 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €1,000, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.89 | 5160.1745 | 9752.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,89 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.81 | 5160.1745 | 4179.74 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,81 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.5 | 1331.74 | 3329.35 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Travel from Norway to Coimbra to start project activities, and outline joint strategies | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
0
Total 1.16: |  |  |  | 28440.55
Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.47 | 5160.1745 | 7585.46 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,47 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.63 | 5160.1745 | 3250.91 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,63 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.9 | 1331.74 | 3862.05 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
0
Total 1.17: |  |  |  | 17264.15
Output / Activity 17 - Analysis of the dynamics of the socio-economic sector
Statistical analysis and desk research and preparation of information collection tools | days | 10 | 182 | 1820 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Carry out of interviews and online surveys | days | 15 | 182 | 2730 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant and base consultant |  | Quaternaire Portugal, SA
Management of online surveys | days | 10 | 79.45 | 794.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management that includes s a base consultant |  | Quaternaire Portugal, SA
Trips for interviews - cost-of-living allowance | days | 20 | 69.19 | 1383.8 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Trips for interviews - travels in mainland | trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Trips for interviews - travels in the Islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Drawing up of final document | days | 5 | 182 | 910 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 40 | 2 | 80 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.18: |  |  |  | 10618.3
Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR
Identification of local players to explore territorial resources (analysis and institutional contacts) | months | 1.5 | 3400.925 | 5101.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Identification of local players to explore resources of territories (through desk research, compilation of information and direct contacts) | months | 6 | 2245.19 | 13471.14 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Direct contacts for information collection | mission | 2 | 476.76 | 953.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
0
0
0
Total 1.19: |  |  |  | 19526.05
Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development
Identification of good practices in R&TD, innovation and entrepreneurship aligned with sustainable development (literature review and institutional contacts) | months | 1.5 | 3400.925 | 5101.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Identification of good practices in R&TD, innovation and entrepreneurship aligned with sustainable development (direct contacts, information compilation and content production for local teams) | months | 6 | 2245.19 | 13471.14 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 2 | 476.76 | 953.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
0
0
0
Total 1.20: |  |  |  | 19526.05
Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability
Preparation of the base document identifying priorities in each BR as a result of Activity 3 | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of focus action groups | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Listening to local players and agents of BRs in the mainland | trip | 15 | 150 | 2250 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Listening to local players and agents of BRs in the islands | trip | 10 | 400 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of Focus Group | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of contributions and results of participatory sessions | days | 15 | 180 | 2700 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of technical content with identification of Priorities for each BR | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 63 | 2 | 126 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.21: |  |  |  | 14945.75
Output / Activity 21 - Selection of key ES for the sustainable development of BR
Travel to the BR of Nordhordland | mission | 1 | 2725 | 2725 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel to design the application of participatory mapping methodology and social and analysis of social and socio-ecological network with partners from Norway (5 days x 2pax) |  | Universidade de Coimbra
Trips to BRs for ES selection | mission | 11 | 1856 | 20416 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for questionnaires, interviews and focus groups (3 days in each BR x 3 pax) |  | Universidade de Coimbra
Miscellaneous consumables (supplies) to support activities | unit | 11 | 100 | 1100 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Consumables necessary for the implementation of the participatory methodology for selection of ES in each of the 11 BRs |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.54 | 5160.1745 | 7946.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,54 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.66 | 5160.1745 | 3405.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,66 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Travel from Nordhordland to Portugal | mission | 1 | 700 | 700 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs from Norway to Portugal |  | Nordhordland Utviklingsselskap IKS
Trips to selected BRs | mission | 4 | 586.38 | 2345.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 4 visits for participation in the participatory methodology (1 days in each BR x 1 pax) |  | Nordhordland Utviklingsselskap IKS
Total 1.22: |  |  |  | 53322.93
Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.54 | 5160.1745 | 7946.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,54 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.66 | 5160.1745 | 3405.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,66 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3 | 1331.74 | 3995.22 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
Total 1.23: |  |  |  | 21669.32
Output / Activity 23 - ES condition / status assessment
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.68 | 5160.1745 | 8669.09 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,68 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.72 | 5160.1745 | 3715.33 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,72 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3 | 1331.74 | 3995.22 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.75 | 1926.15 | 3370.76 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.75 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
Total 1.24: |  |  |  | 22316.13
Output / Activity 24 - ES valuation proposal (add value)
Trips to BRs for the definition of strategies of Valorisation and Valuation of ES | mission | 11 | 1238 | 13618 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for questionnaires, interviews and focus groups (3 days in each BR x 2 pax) |  | Universidade de Coimbra
Miscellaneous consumables (supplies) to support activities | unit | 11 | 100 | 1100 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Consumables necessary for the implementation of participatory methodology for valuing and valuing ES in each of the 11 BRs |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.61 | 5160.1745 | 8307.88 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,61 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.69 | 5160.1745 | 3560.52 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,69 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.8 | 1331.74 | 2397.13 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.8 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Travel from Nordhordland to Portugal | mission | 1 | 700 | 700 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs from Norway to Portugal |  | Nordhordland Utviklingsselskap IKS
Trips to selected BRs | mission | 4 | 586.38 | 2345.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 4 visits for participation in the participatory methodology (1 days in each BR x 1 pax) |  | Nordhordland Utviklingsselskap IKS
0
0
Total 1.25: |  |  |  | 40426.78
Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action
Consultancy in the area of valuation of ES | unit | 11 | 900 | 9900 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Specialised consultancy in the field of valuation of ES and methodologies and ways of calculating economic and natural value (2 consultants x 11 months consulting) |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 8.85 | 1926.15 | 17046.43 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 8.85 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.26: |  |  |  | 26946.43
Output / Activity 26 - Mapping BR ES
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 2.03 | 5160.1745 | 10475.16 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 2.03 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.87 | 5160.1745 | 4489.35 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,87 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.9 | 1331.74 | 3862.05 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.65 | 1926.15 | 3178.15 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.65 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
0
0
0
0
0
Total 1.27: |  |  |  | 30402.44
Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.98 | 5160.1745 | 5056.97 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,98 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.42 | 5160.1745 | 2167.27 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,42 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.85 | 1926.15 | 3563.38 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.85 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.28: |  |  |  | 10787.62
Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.75 | 5160.1745 | 9030.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,75 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.75 | 5160.1745 | 3870.13 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,75 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44c |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3.2 | 1331.74 | 4261.57 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3.2 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 2.05 | 1926.15 | 3948.61 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.05 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Travel from Norway to Coimbra to collaborate in the modelling of ES | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
0
0
0
Total 1.29: |  |  |  | 27661.35
Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action
Trip to BR for selection of ES to mitigate and adapt to climate change | mission | 11 | 1238 | 13618 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for the application of the participatory methodology (3 days in each BR x 2 pax). These trips will also serve for the development of activity 73 (Awareness-raising Actions about ES) |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.19 | 5160.1745 | 6140.61 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1.19 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.51 | 5160.1745 | 2631.69 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,51 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.7 | 1331.74 | 2263.96 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
Total 1.30: |  |  |  | 30975.98
Output / Activity 30 - ES Sustainable Management Manual for BR
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0.36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.31: |  |  |  | 8722.52
Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR
Development and combination of the different contributions of the team and participatory sessions for the contents of the SDPs | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the 11 SDPs | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of participatory discussion sessions | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Islands | trip | 8 | 400 | 3200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 20 | 69.19 | 1383.8 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of participatory discussion sessions | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of contributions and results of participatory sessions | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 71 | 2 | 142 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.32: |  |  |  | 12285.8
Output / Activity 32 - SDP public presentations and discussions
Organisation of public discussion sessions | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Mainland | trip | 10 | 150 | 1500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Islands | trip | 8 | 400 | 3200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 16 | 69.19 | 1107.04 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of public discussion sessions | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation, systematisation and consideration of contributions and results of the public discussion period | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Validation of the consideration and formalisation of the respective report | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 45 | 2 | 90 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.33: |  |  |  | 11117.04
Output / Activity 33 - Revision and editing of the final versions of the SDP
Modification of the SDPs according to the consideration of public participation and the follow-up and evaluation of pilot actions | days | 22 | 180 | 3960 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Non-technical summary of SDPs highlighting strategy success factors | days | 10 | 200 | 2000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 32 | 2 | 64 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.34: |  |  |  | 6024
Output / Activity 34 - Selection of 11 pilot actions
Definition of a matrix of selection criteria for pilot actions | days | 1 | 180 | 180 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Reflection and discussion among partners on the impact on BR actions | days | 1 | 200 | 200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Proposal of pilot actions by BR | days | 1 | 2 | 2 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.35: |  |  |  | 382
Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action
Survey and initial recognition of BRs | days | 23 | 121.86 | 2802.78 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Development of Tourist Guidebooks | days | 33 | 121.86 | 4021.38 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Technical work in BRs - cost-of-living allowance | days | 40 | 69.19 | 2767.6 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Technical work in BRs - trips on the Mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Technical work in BRs - trips to the Islands | trip | 10 | 400 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical development of tourist guidebooks (research, organisation, writing) | days | 45 | 121.86 | 5483.7 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant. In conjunction with Communication actions (fan trips and participation in tourism fairs) |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.36: |  |  |  | 20875.46
Output / Activity 36 - Memories and identities - systematic record of memories
Training actions | days | 11 | 1230 | 13530 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | 11 training actions (2 days in each BR x 3 pax) |  | Universidade Nova de Lisboa
Presentation trips | days | 11 | 1590 | 17490 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for presentation of the project in each of the 11 reserves (3pax per session) |  | Universidade Nova de Lisboa
Training trips | days | 11 | 1590 | 17490 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips to training sessions in each of the 11 reserves (3 PAX per session) |  | Universidade Nova de Lisboa
Interview trips | days | 11 | 1270 | 13970 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips to collect memories in each of the 11 reserves (5 days per BR; 2 PAX) |  | Universidade Nova de Lisboa
Validation of interviews trips | days | 11 | 425 | 4675 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for validation of interviews in each of 11 reserves (2 days per BR; 1 PAX) |  | Universidade Nova de Lisboa
Audiovisual recording equipment | numeric | 3 | 2510 | 7530 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Interview storage equipment | numeric | 6 | 150 | 900 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Audiovisual editing software | numeric | 1 | 999.9 | 999.9 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Technical Editing of Content | hours | 660 | 18.45 | 12177 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
App for recording memories | numeric | 1 | 18450 | 18450 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for the development of an app for registration and management of intangible cultural heritage (memories) |  | Universidade Nova de Lisboa
HR (researchers) | numeric | 1 | 9568 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); preparation and carry out of interviews; analysis of the contents of the interviews |  | Universidade Nova de Lisboa
Total 1.37: |  |  |  | 116779.9
Output / Activity 37 - Creation of memory and community spaces - pilot action
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the build-up of memory spaces in pilot reserve |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.38: |  |  |  | 6082
Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action
Design, development of the concept and model of the store network for the Biosphere Reserves | days | 30 | 182 | 5460 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 25 | 2 | 50 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
0
Total 1.39: |  |  |  | 5510
Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks
Identifying the different indicator systems used in BR and the best practices implemented | days | 20 | 180 | 3600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Contacts with international partners | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Three case studies | days | 15 | 180 | 2700 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 84 | 2 | 168 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.40: |  |  |  | 7668
Output / Activity 40 - Architecture of SDP indicators and monitoring system
Definition of the system of indicators for the national network and for each BR | days | 15 | 200 | 3000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Identification of the sources of information to be mobilised | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Definition of data collection locations and their frequency | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Specification of techniques and equipment for data collection | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Especificação de critérios de avaliação/ Specification of evaluation criteria | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of entities involved for the provision of information and active participation in the collection and input of the monitoring plan | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Development of datasheets by indicator | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the monitoring plan/indicator system | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 70 | 2 | 140 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.41: |  |  |  | 13040
Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system
Organisation of the presentation session of monitoring plans/indicator system | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Submission of monitoring plans/indicator system to the Supervising Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of contributions received | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Development of the final version of monitoring plans/indicator system | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 24 | 2 | 48 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.42: |  |  |  | 4408
Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System
Design of the training programme | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 2 | 150 | 300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 6 | 69.19 | 415.14 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 3 | 220 | 660 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 23 | 2 | 46 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.43: |  |  |  | 8021.14
Output / Activity 43 - Citizen Science for sustainable BR - pilot action
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the promotion of citizen science activities with the Reserves, and in collaboration with the National Network of Citizen Science |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.44: |  |  |  | 2392
Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves
Architecture and selection of representative indicators to be integrated in the barometer from the perspective of management and communication | days | 10 | 200 | 2000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Validation of the proposal with the Supervising Committee | days | 3 | 200 | 600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Generation of reports | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Generation of graphic elements for communication and training actions | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 27 | 2 | 54 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.45: |  |  |  | 5174
Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves
Development of technical design | days | 30 | 121.86 | 3655.8 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Benchmarking analysis | days | 10 | 121.86 | 1218.6 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Training actions in the scope of certification and good practices in Sustainable Tourism: face-to-face (practical component) and online (general content) | days | 44 | 121.86 | 5361.84 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Quaternaire Portugal, SA
Technical work with BR managers - cost-of-living allowance | days | 22 | 69.19 | 1522.18 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Technical work with BR managers - trips on the Mainland | trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the mainland |  | Quaternaire Portugal, SA
Technical work with BR managers - trips to the Islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the islands |  | Quaternaire Portugal, SA
Design, organisation and drafting of the Sustainable Tourism Guidebook | days | 15 | 121.86 | 1827.9 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Quaternaire Portugal, SA
0
0
0
Total 1.46: |  |  |  | 16486.32
Output / Activity 46 - Assessment of training needs that will support the training planing
Design of the methodological strategy of diagnosis | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Collection of diagnostic support information | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of the diagnostic of training needs | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of Training Plans for the 11 Reserves | days | 22 | 220 | 4840 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the mainland |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the islands |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | cost-of-living allowances | 33 | 69.19 | 2283.27 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Use of computer equipment | days | 87 | 2 | 174 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.47: |  |  |  | 23747.27
Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents.
Design of the training programme | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 1 | 400 | 400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for trainees from the islands |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 33 | 69.19 | 2283.27 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 3 | 220 | 660 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 28 | 2 | 56 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.48: |  |  |  | 11349.27
Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP.
Design of the training programme | days | 10 | 220 | 2200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 20 | 220 | 4400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 1 | 400 | 400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for trainees from the islands |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 44 | 69.19 | 3044.36 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 35 | 2 | 70 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.49: |  |  |  | 14764.36
Output / Activity 49 - Training associated with the implementation of pilot actions
Analysis and monitoring of pilot actions and identification of new skills | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of the analysis report and development of a plan for the dissemination of new competences related to pilot actions | days | 22 | 220 | 4840 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Actions to disseminate new competencies | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for the technical team on the mainland |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs of the technical team on the islands |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | cost-of-living allowances | 30 | 69.19 | 2075.7 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Use of computer equipment | days | 67 | 2 | 134 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
Total 1.50: |  |  |  | 19099.7
Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities
Design and coordination of the training of local teams | months | 4 | 3400.925 | 13603.7 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Support of local BR teams, during and after training, to carry out activities to support economic initiative, search for partnerships (companies and other stakeholders) and financing, both public and private. | months | 9 | 2245.19 | 20206.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Carrying out online training | months | 1 | 2245.19 | 2245.19 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 trainers |  | Instituto Pedro Nunes, AIDCT
Creation of training materials | numeric | 1 | 750 | 750 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | training materials |  | Instituto Pedro Nunes, AIDCT
Zoom License | months | 12 | 13.99 | 167.88 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Zoom License |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 4 | 476.76 | 1907.04 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
Total 1.51: |  |  |  | 38880.52
Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.05 | 5160.1745 | 5418.18 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,05 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.45 | 5160.1745 | 2322.08 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,45 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
0
0
0
0
0
0
0
Total 1.52: |  |  |  | 16137.99
Output / Activity 52 - Technical workshop on ecosystem services
Printing material and consumables | person | 60 | 10 | 600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Printing of supporting material, including technical documents, and consumables (notebooks, pens, folders, etc.) to support for the workshop |  | Universidade de Coimbra
Catering service (including lunch and 2 coffee-breaks) | person | 60 | 25 | 1500 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Catering service for the workshop, including lunch and 2 coffee-breaks for 50 people |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Trips for active participation in the workshop | mission | 1 | 1450 | 1450 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost includes travel from Norway to Portugal, 8 days of cost-of-living allowance and 7 nights stay for 1 person, who will participate in the organisation of the workshop |  | Nordhordland Utviklingsselskap IKS
Travel from Norway to Coimbra to participate in the organisation of the workshop | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
Total 1.53: |  |  |  | 24655.25
Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action
Design and coordination of the training of local entrepreneurship projects | months | 4.5 | 3400.925 | 15304.16 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Entrepreneurs' support, during the post-training, to explore the commercial validity of their project, to seek partnerships and sources of funding | months | 9 | 2245.19 | 20206.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Carrying out online training | months | 5 | 2245.19 | 11225.95 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 trainers |  | Instituto Pedro Nunes, AIDCT
Creation of training materials | numeric | 1 | 3500 | 3500 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Training materials |  | Instituto Pedro Nunes, AIDCT
Online workshops and trainings | months | 24 | 13.99 | 335.76 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Zoom License |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 6 | 715.14 | 4290.84 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
Total 1.54: |  |  |  | 54863.42
Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries
Follow-up of the Visits programme | days | 5 | 121.86 | 609.3 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Participation in the Visits programme | days | 4 | 1250 | 5000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Icelandic National Commission for UNESCO
Carrying out visits - trips on the mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips on the mainland |  | Quaternaire Portugal, SA
Carrying out visits - trips to the islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips on the islands |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.55: |  |  |  | 9409.3
Output / Activity 55 - Final project seminar
Follow-up of the organisation of the final Seminary | days | 15 | 121.86 | 1827.9 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Participation in the final Seminar | days | 4 | 1250 | 5000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Icelandic National Commission for UNESCO
Organisation and production of the final seminar | event | 1 | 30000 | 30000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | hiring a company specialised in events |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.56: |  |  |  | 36827.9
Output / Activity 56 - Marketing Strategy Development
Coordination of the development of the marketing strategy | hour | 70 | 112.5 | 7875 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development of marketing strategy | hour | 25 | 40 | 1000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for the design and development of the marketing strategy | hour | 80 | 5 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 44 | 69.19 | 3044.36 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 22 | 150 | 3300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
Total 1.57: |  |  |  | 17219.36
Output / Activity 57 - Communication Plan Design
Coordination of the development of the communication plan | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development of communication plan | hour | 50 | 80 | 4000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services - 2 consultants |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work on the development of the communication plan | hour | 110 | 5 | 550 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 30 | 150 | 4500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
Total 1.58: |  |  |  | 17442.25
Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook)
Coordination of development | hour | 70 | 112.5 | 7875 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 80 | 80 | 6400 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 280 | 5 | 1400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 5 | 69.19 | 345.95 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 5 | 150 | 750 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.59: |  |  |  | 16770.95
Output / Activity 59 - Generic Creative Development
Coordination of development | hour | 60 | 112.5 | 6750 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 120 | 80 | 9600 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 130 | 5 | 650 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 5 | 69.19 | 345.95 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 5 | 150 | 750 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.60: |  |  |  | 18095.95
Output / Activity 60 - Creative development of digital communication
Coordination of development | hour | 50 | 112.5 | 5625 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 80 | 80 | 6400 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 90 | 5 | 450 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 2 | 69.19 | 138.38 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 2 | 150 | 300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.61: |  |  |  | 12913.38
Output / Activity 61 - Productions and promotional materials - Offline
Coordination of development | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 125 | 45 | 5625 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 50 | 5 | 250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Promotion materials (offline) | Set of communication items to be produced within the scope of the activity | 1 | 78500 | 78500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.62: |  |  |  | 89437.5
Output / Activity 62 - Productions and promotional materials - Online
Coordination of development | hour | 50 | 112.5 | 5625 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 125 | 45 | 5625 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Promotion materials (on line) | Set of communication items to be produced within the scope of the activity | 1 | 52000 | 52000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
0
Total 1.63: |  |  |  | 63250
Output / Activity 63 - Productions and promotional materials - Audiovisual materials
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 75 | 45 | 3375 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 40 | 5 | 200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Audiovisual Materials | Set of communication items to be produced within the scope of the activity | 1 | 13500 | 13500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.64: |  |  |  | 18762.5
Output / Activity 64 - Brand Activations
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 225 | 45 | 10125 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 30 | 5 | 150 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 15 | 150 | 2250 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missões / missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
Brand Activations | Set of communication items to be produced within the scope of the activity | 1 | 17500 | 17500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
Total 1.65: |  |  |  | 35042.25
Output / Activity 65 - Public Relations
Coordination of development | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 150 | 25 | 3750 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 10 | 69.19 | 691.9 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 10 | 150 | 1500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
Public relations | months | 20 | 825 | 16500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of acquired services is only an estimation (fees/month) |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
Total 1.66: |  |  |  | 28679.4
Output / Activity 66 - Media Strategy and Planning
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
0
0
0
Total 1.67: |  |  |  | 1687.5
Output / Activity 67 - Media Strategy and Planning - Press
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 50 | 25 | 1250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Press | advertisements and other advertising media | 1 | 13300 | 13300 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.68: |  |  |  | 17175
Output / Activity 68 - Media Strategy and Planning - Radio
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Valor/hora médio de 2019/ Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 50 | 25 | 1250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 50 | 5 | 250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Digital | advertisements and other advertising media | 1 | 13500 | 13500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.69: |  |  |  | 17250
Output / Activity 69 - Media Strategy and Planning - Digital
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 250 | 25 | 6250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Digital | advertisements and other advertising media | 1 | 43500 | 43500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.70: |  |  |  | 52375
Output / Activity 70 - Culture and Education Agenda
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of a cultural and educational agenda |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.71: |  |  |  | 2392
Output / Activity 71 - Development of Awareness Plan for different audiences
Technical Development | days | 10 | 122.83 | 1228.3 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
0
0
Total 1.72: |  |  |  | 1228.3
Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners
Organisation of presentation sessions | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Presentation discussion session in the BRs of the Mainland | trip | 8 | 150 | 1200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Presentation discussion session in the BRs of the Islands | deslocação / trip | 6 | 400 | 2400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 14 | 69.19 | 968.66 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Use of computer equipment | days | 16 | 2 | 32 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.73: |  |  |  | 4960.66
Output / Activity 73 - ES awareness actions
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 0.8 | 1331.74 | 1065.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.74: |  |  |  | 7257.6
Output / Activity 74 - Planning of the National Biosphere Olympics
Olympiads planning: Development of regulations, preparation of tests, planning of logistics and scientific part, including formation of commissions | months | 2 | 500 | 1000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human resources, staff of the Order of Biologists |  | Ordem dos Biólogos
Human Resources | months | 3 | 1193.89 | 3581.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Hiring a Master for logistic support |  | Ordem dos Biólogos
0
0
0
0
0
0
0
0
Total 1.75: |  |  |  | 4581.67
Output / Activity 75 - Communication and dissemination of the BR Olympics
Promotion process for the Olympiad, including production and distribution of posters and preparation of the dedicated website for registration and information | months | 1 | 500 | 500 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human resources, staff of the Order of Biologists |  | Ordem dos Biólogos
Acquisition of services: material for tests, communications | months | 5 | 800 | 4000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
0
0
0
0
0
0
0
0
Total 1.76: |  |  |  | 4500
Output / Activity 76 - BR Olympics
Recursos Humanos/ Human Resources | months | 3 | 1193.89 | 3581.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Hiring a Master for logistic support |  | Ordem dos Biólogos
Trips for students and organisation staff for the final | people to transport | 50 | 80 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b |  |  | Ordem dos Biólogos
Accommodation for participants | rooms/overnight stays | 100 | 50 | 5000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Accommodation hiring |  | Ordem dos Biólogos
Food - meals during the final test | meals | 400 | 15 | 6000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
Trophies and prises for the winners | trophies | 50 | 60 | 3000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
Merchandising - T-shirts, vests, backpacks, banners, roll-ups, flyers | articles | 200 | 20 | 4000 | Costs of consumables and supplies - Reg. Art. 8.3.1.e |  |  | Ordem dos Biólogos
Jury support | members of the jury | 8 | 375 | 3000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b |  |  | Ordem dos Biólogos
0
0
0
Total 1.77: |  |  |  | 28581.67
Output / Activity 77 - Design and organization of Biosphere Reserve Festivals
Design and structuring of Festivals | days | 40 | 130 | 5200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of Festivals | days | 40 | 130 | 5200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - cost-of-living allowance | days | 22 | 69.19 | 1522.18 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - trips in mainland | deslocação / trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - trips to the islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Use of computer equipment | days | 30 | 2 | 60 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.78: |  |  |  | 14882.18
Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB
BioKeepers activity management (HR) | months | 12 | 1800 | 21600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Contract Project management; Relationship with schools; BioKeepers |  | KEEP - Knowledge for Peace, People and the Planet, Association
Presentation trips | days | 11 | 430 | 4730 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for presentation and awareness-raising of communities about the BioKeepers activity |  | KEEP - Knowledge for Peace, People and the Planet, Association
0
0
0
0
0
0
0
0
Total 1.79: |  |  |  | 26330
Output / Activity 79 - Atlas of Portuguese Biosphere reserves
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); research for and preparation of contents for the development of an Atlas of Biosphere Reserves |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.80: |  |  |  | 13258
Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension
Management of Activity of Extension of Knowledge (HR) | months | 18 | 1800 | 32400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Contract Project management; Relationship with schools and local entitie |  | KEEP - Knowledge for Peace, People and the Planet, Association
Trips Coordination | days | 11 | 1310 | 14410 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 14 days of face-to-face-coordination for each reserve |  | KEEP - Knowledge for Peace, People and the Planet, Association
0
0
0
0
0
0
0
0
Total 1.81: |  |  |  | 46810
Output / Activity 81 - Itinerant exhibition
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the organisation and management of contents for the travelling exhibition |  | Universidade Nova de Lisboa
Revision of texts | numérico / numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.82: |  |  |  | 6082
Total 1: |  |  |  | 1944647.27
2. INDIRECT COSTS*
Total 2: |  |  |  | 254019.18
TOTAL Project COST (1 + 2): |  |  |  | 2198666.45
Total project management cost (€): |  |  |  | 316740.16
Total output related cost (€): |  |  |  | 1627907.11
Output / Activity Budget Heading | Management cost | Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR) | Output / Activity 2 - Survey of existing BR action plans, objectives and priorities. | Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks | Output / Activity 4 - History of BR | Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access | Output / Activity 6 - Auscultation / Perception and identification of heritage | Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR | Output / Activity 8 - Development of the participatory planning methodology for the SDP | Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP | Output / Activity 10 - Digital Infrastructure - distributed management model | Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website | Output / Activity 12 - Digital infrastructure - Indicators management dashboard | Output / Activity 13 - Digital Infrastructure - Research Data Catalog | Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves | Output / Activity 15 - Mapping the BR ecosystem diversity | Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems | Output / Activity 17 - Analysis of the dynamics of the socio-economic sector | Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR | Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development | Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability | Output / Activity 21 - Selection of key ES for the sustainable development of BR | Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES | Output / Activity 23 - ES condition / status assessment | Output / Activity 24 - ES valuation proposal (add value) | Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action | Output / Activity 26 - Mapping BR ES | Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization | Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures | Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action | Output / Activity 30 - ES Sustainable Management Manual for BR | Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR | Output / Activity 32 - SDP public presentations and discussions | Output / Activity 33 - Revision and editing of the final versions of the SDP | Output / Activity 34 - Selection of 11 pilot actions | Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action | Output / Activity 36 - Memories and identities - systematic record of memories | Output / Activity 37 - Creation of memory and community spaces - pilot action | Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action | Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks | Output / Activity 40 - Architecture of SDP indicators and monitoring system | Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system | Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System | Output / Activity 43 - Citizen Science for sustainable BR - pilot action | Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves | Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves | Output / Activity 46 - Assessment of training needs that will support the training planing | Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents. | Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP. | Output / Activity 49 - Training associated with the implementation of pilot actions | Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities | Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans | Output / Activity 52 - Technical workshop on ecosystem services | Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action | Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries | Output / Activity 55 - Final project seminar | Output / Activity 56 - Marketing Strategy Development | Output / Activity 57 - Communication Plan Design | Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook) | Output / Activity 59 - Generic Creative Development | Output / Activity 60 - Creative development of digital communication | Output / Activity 61 - Productions and promotional materials - Offline | Output / Activity 62 - Productions and promotional materials - Online | Output / Activity 63 - Productions and promotional materials - Audiovisual materials | Output / Activity 64 - Brand Activations | Output / Activity 65 - Public Relations | Output / Activity 66 - Media Strategy and Planning | Output / Activity 67 - Media Strategy and Planning - Press | Output / Activity 68 - Media Strategy and Planning - Radio | Output / Activity 69 - Media Strategy and Planning - Digital | Output / Activity 70 - Culture and Education Agenda | Output / Activity 71 - Development of Awareness Plan for different audiences | Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners | Output / Activity 73 - ES awareness actions | Output / Activity 74 - Planning of the National Biosphere Olympics | Output / Activity 75 - Communication and dissemination of the BR Olympics | Output / Activity 76 - BR Olympics | Output / Activity 77 - Design and organization of Biosphere Reserve Festivals | Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB | Output / Activity 79 - Atlas of Portuguese Biosphere reserves | Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension | Output / Activity 81 - Itinerant exhibition | Custo total de despesas elegíveis / TOTAL ELIGIBLE BUDGET HEADING COSTS | % total custos elegíveis / % TOTAL ELIGIBLE COSTS
Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 275714.1 | 4680 | 13860 | 8000 | 9568 | 2392 | 2392 | 8040 | 5780 | 1840 | 2392 | 0 | 0 | 2392 | 9568 | 19827.55 | 17264.15 | 6254.5 | 18572.53 | 18572.53 | 6840 | 26036.41 | 21669.32 | 22316.13 | 22663.26 | 17046.43 | 30402.44 | 10787.62 | 23676.35 | 17357.98 | 8722.52 | 5760 | 5220 | 5960 | 380 | 12307.86 | 9568 | 2392 | 5460 | 7500 | 12900 | 4360 | 7260 | 2392 | 5120 | 12064.14 | 19140 | 7260 | 9900 | 14740 | 36055.6 | 16137.99 | 17120.25 | 46736.82 | 5609.3 | 6827.9 | 8275 | 5612.5 | 9275 | 7400 | 6075 | 5312.5 | 5625 | 1887.5 | 1837.5 | 5437.5 | 1687.5 | 2625 | 2500 | 2625 | 2392 | 1228.3 | 360 | 7257.6 | 4581.67 | 500 | 3581.67 | 10400 | 21600 | 9568 | 32400 | 2392 | 1075235.92 | 48.9%
Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 22578.5 | 0 | 0 | 0 | 7900 | 0 | 9480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3985 | 0 | 4283.8 | 953.52 | 953.52 | 7979.75 | 26186.52 | 0 | 0 | 16663.52 | 0 | 0 | 0 | 3985 | 13618 | 0 | 6383.8 | 5807.04 | 0 | 0 | 8567.6 | 53625 | 0 | 0 | 0 | 0 | 0 | 715.14 | 0 | 0 | 4422.18 | 4433.27 | 4033.27 | 4794.36 | 4225.7 | 1907.04 | 0 | 6035 | 4290.84 | 3800 | 0 | 7944.36 | 7829.75 | 1095.95 | 1095.95 | 438.38 | 0 | 0 | 0 | 5579.75 | 2991.9 | 0 | 0 | 0 | 0 | 0 | 0 | 4568.66 | 0 | 0 | 0 | 7000 | 4422.18 | 4730 | 0 | 14410 | 0 | 293714.25 | 13.36%
Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | 2902.5 | 56 | 110 | 88 | 0 | 0 | 0 | 84 | 62 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 90 | 64 | 2 | 0 | 0 | 0 | 50 | 168 | 140 | 48 | 46 | 0 | 54 | 0 | 174 | 56 | 70 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 4858.5 | 0.221%
Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | 4950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9429.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19007.9 | 0.8645%
Purchase of land and real estate - Reg. Art. 8.3.1.d & Art. 8.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Costs of consumables and supplies - Reg. Art. 8.3.1.e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917.88 | 0 | 1500 | 3835.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 12453.64 | 0.5664%
Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | 7875.06 | 0 | 0 | 0 | 9840 | 0 | 0 | 0 | 0 | 0 | 0 | 64575 | 24600 | 0 | 3690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44157 | 3690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1000 | 4000 | 6400 | 9600 | 6400 | 84125 | 57625 | 16875 | 27625 | 20250 | 0 | 14550 | 14750 | 49750 | 0 | 0 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 3690 | 0 | 3690 | 536657.06 | 24.41%
Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | 2720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2720 | 0.1237%
INDIRECT COSTS - Reg. Art. 8.5 | [82 empty] | 254019.18 | 11.55%
TOTAL ELIGIBLE COSTS | 316740.16 | 4736 | 13970 | 8088 | 27308 | 2392 | 11872 | 8124 | 5842 | 1860 | 2392 | 64575 | 24600 | 2392 | 13258 | 28440.55 | 17264.15 | 10618.3 | 19526.05 | 19526.05 | 14945.75 | 53322.93 | 21669.32 | 22316.13 | 40426.78 | 26946.43 | 30402.44 | 10787.62 | 27661.35 | 30975.98 | 8722.52 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 116779.9 | 6082 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 2392 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 38880.52 | 16137.99 | 24655.25 | 54863.42 | 9409.3 | 36827.9 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 2392 | 1228.3 | 4960.66 | 7257.6 | 4581.67 | 4500 | 28581.67 | 14882.18 | 26330 | 13258 | 46810 | 6082 | 2198666.45
% TOTAL PROJECT COSTS | 14.41% | 0.2154% | 0.6354% | 0.3679% | 1.242% | 0.1088% | 0.54% | 0.3695% | 0.2657% | 0.0846% | 0.1088% | 2.937% | 1.119% | 0.1088% | 0.603% | 1.294% | 0.7852% | 0.4829% | 0.8881% | 0.8881% | 0.6798% | 2.425% | 0.9856% | 1.015% | 1.839% | 1.226% | 1.383% | 0.4906% | 1.258% | 1.409% | 0.3967% | 0.5588% | 0.5056% | 0.274% | 0.01737% | 0.9495% | 5.311% | 0.2766% | 0.2506% | 0.3488% | 0.5931% | 0.2005% | 0.3648% | 0.1088% | 0.2353% | 0.7498% | 1.08% | 0.5162% | 0.6715% | 0.8687% | 1.768% | 0.734% | 1.121% | 2.495% | 0.428% | 1.675% | 0.7832% | 0.7933% | 0.7628% | 0.823% | 0.5873% | 4.068% | 2.877% | 0.8534% | 1.594% | 1.304% | 0.07675% | 0.7812% | 0.7846% | 2.382% | 0.1088% | 0.05587% | 0.2256% | 0.3301% | 0.2084% | 0.2047% | 1.3% | 0.6769% | 1.198% | 0.603% | 2.129% | 0.2766% | 100%
Output / Activity Project Promoter / Partner | Management cost | Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR) | Output / Activity 2 - Survey of existing BR action plans, objectives and priorities. | Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks | Output / Activity 4 - History of BR | Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access | Output / Activity 6 - Auscultation / Perception and identification of heritage | Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR | Output / Activity 8 - Development of the participatory planning methodology for the SDP | Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP | Output / Activity 10 - Digital Infrastructure - distributed management model | Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website | Output / Activity 12 - Digital infrastructure - Indicators management dashboard | Output / Activity 13 - Digital Infrastructure - Research Data Catalog | Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves | Output / Activity 15 - Mapping the BR ecosystem diversity | Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems | Output / Activity 17 - Analysis of the dynamics of the socio-economic sector | Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR | Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development | Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability | Output / Activity 21 - Selection of key ES for the sustainable development of BR | Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES | Output / Activity 23 - ES condition / status assessment | Output / Activity 24 - ES valuation proposal (add value) | Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action | Output / Activity 26 - Mapping BR ES | Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization | Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures | Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action | Output / Activity 30 - ES Sustainable Management Manual for BR | Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR | Output / Activity 32 - SDP public presentations and discussions | Output / Activity 33 - Revision and editing of the final versions of the SDP | Output / Activity 34 - Selection of 11 pilot actions | Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action | Output / Activity 36 - Memories and identities - systematic record of memories | Output / Activity 37 - Creation of memory and community spaces - pilot action | Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action | Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks | Output / Activity 40 - Architecture of SDP indicators and monitoring system | Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system | Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System | Output / Activity 43 - Citizen Science for sustainable BR - pilot action | Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves | Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves | Output / Activity 46 - Assessment of training needs that will support the training planing | Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents. | Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP. | Output / Activity 49 - Training associated with the implementation of pilot actions | Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities | Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans | Output / Activity 52 - Technical workshop on ecosystem services | Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action | Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries | Output / Activity 55 - Final project seminar | Output / Activity 56 - Marketing Strategy Development | Output / Activity 57 - Communication Plan Design | Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook) | Output / Activity 59 - Generic Creative Development | Output / Activity 60 - Creative development of digital communication | Output / Activity 61 - Productions and promotional materials - Offline | Output / Activity 62 - Productions and promotional materials - Online | Output / Activity 63 - Productions and promotional materials - Audiovisual materials | Output / Activity 64 - Brand Activations | Output / Activity 65 - Public Relations | Output / Activity 66 - Media Strategy and Planning | Output / Activity 67 - Media Strategy and Planning - Press | Output / Activity 68 - Media Strategy and Planning - Radio | Output / Activity 69 - Media Strategy and Planning - Digital | Output / Activity 70 - Culture and Education Agenda | Output / Activity 71 - Development of Awareness Plan for different audiences | Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners | Output / Activity 73 - ES awareness actions | Output / Activity 74 - Planning of the National Biosphere Olympics | Output / Activity 75 - Communication and dissemination of the BR Olympics | Output / Activity 76 - BR Olympics | Output / Activity 77 - Design and organization of Biosphere Reserve Festivals | Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB | Output / Activity 79 - Atlas of Portuguese Biosphere reserves | Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension | Output / Activity 81 - Itinerant exhibition | TOTAL ELIGIBLE BUDGET HEADING COSTS | % TOTAL ELIGIBLE COSTS
Quaternaire Portugal, SA | 316740.16 | 4736 | 13970 | 8088 | 0 | 0 | 0 | 8124 | 5842 | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10618.3 | 0 | 0 | 14945.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 0 | 0 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 0 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 0 | 0 | 0 | 0 | 4409.3 | 31827.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228.3 | 4960.66 | 0 | 0 | 0 | 0 | 14882.18 | 0 | 0 | 0 | 0 | 622184.91 | 31.99%
Universidade de Coimbra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21889.82 | 14698.42 | 0 | 0 | 0 | 0 | 41879.68 | 19103.59 | 19750.4 | 28983.53 | 26946.43 | 22004.71 | 10787.62 | 21110.62 | 28410.25 | 8722.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7740.26 | 10822.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7257.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290107.97 | 14.92%
Universidade Nova de Lisboa | 0 | 0 | 0 | 0 | 27308 | 2392 | 11872 | 0 | 0 | 0 | 2392 | 64575 | 24600 | 2392 | 13258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116779.9 | 6082 | 0 | 0 | 0 | 0 | 0 | 2392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13258 | 0 | 6082 | 295774.9 | 15.21%
PC&A - Consultores de Marketing Estratégico, Lda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406101.04 | 20.88%
Instituto Pedro Nunes, AIDCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19526.05 | 19526.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38880.52 | 0 | 0 | 54863.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132796.04 | 6.829%
Ordem dos Biólogos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581.67 | 4500 | 28581.67 | 0 | 0 | 0 | 0 | 0 | 37663.34 | 1.937%
KEEP - Knowledge for Peace, People and the Planet, Association | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26330 | 0 | 46810 | 0 | 73140 | 3.761%
University of Bergen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6550.73 | 2565.73 | 0 | 0 | 0 | 0 | 2565.73 | 2565.73 | 2565.73 | 2565.73 | 0 | 2565.73 | 0 | 6550.73 | 2565.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565.73 | 6550.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40178.03 | 2.066%
Nordhordland Utviklingsselskap IKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8877.52 | 0 | 0 | 8877.52 | 0 | 5832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5832 | 7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36701.04 | 1.887%
Icelandic National Commission for UNESCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0.5142%
TOTAL ELIGIBLE COSTS | 316740.16 | 4736 | 13970 | 8088 | 27308 | 2392 | 11872 | 8124 | 5842 | 1860 | 2392 | 64575 | 24600 | 2392 | 13258 | 28440.55 | 17264.15 | 10618.3 | 19526.05 | 19526.05 | 14945.75 | 53322.93 | 21669.32 | 22316.13 | 40426.78 | 26946.43 | 30402.44 | 10787.62 | 27661.35 | 30975.98 | 8722.52 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 116779.9 | 6082 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 2392 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 38880.52 | 16137.99 | 24655.25 | 54863.42 | 9409.3 | 36827.9 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 2392 | 1228.3 | 4960.66 | 7257.6 | 4581.67 | 4500 | 28581.67 | 14882.18 | 26330 | 13258 | 46810 | 6082 | 1944647.27
* SEE 9.ELIGIBILITY OF EXPENDITURE ; **SEE 16. ADDITIONAL INFORMATION

## 09_Call#3_Budget
ANNEX I PROJECT 09_CALL#3 Biosphere Reserves: Sustainable Territories, Resilient communities
d) Budget
Programme: | Environment, Climate Change and Low Carbon Economy Programme
Project title: | Biosphere Reserves: sustainable territories, resilient communities
Project Promoter: | Quaternaire Portugal, SA
Total project cost: | 2198666.46
Project grant rate: | 100%
Project duration: | 30 months
| Unit | Number of units (a) | Unit price (€) (b) | Total cost (€) (a) x (b) | Type of expenditure | Comments/ Additional information | Guidance** | Project Promoter / Partner
1. DIRECT EXPENDITURES*
Management cost
Technical-scientific coordination of the project | months | 30 | 4787 | 143610 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 70% of the time |  | Quaternaire Portugal, SA
Executive coordination of the project | months | 30 | 920 | 27600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 15% of the time |  | Quaternaire Portugal, SA
Support for executive coordination | months | 30 | 1942 | 58260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of 60% of the time |  | Quaternaire Portugal, SA
Management and administrative team assigned to the project | months | 30 | 1565.5 | 46965 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Monthly value/considering an allocation of one element at 16% and another at 40% of the time |  | Quaternaire Portugal, SA
Provision of analytical accounting services within the scope of the project | months | 30 | 216.462 | 6493.86 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Service Agreement contract (fees and license fee for the analytical accounting software) |  | Quaternaire Portugal, SA
Trips of project coordination, management and administrative teams | trip | 40 | 150 | 6000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs of the coordination, management and administrative teams on the mainland |  | Quaternaire Portugal, SA
Trips of project coordination | trip | 20 | 400 | 8000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Costs of trips of the coordination and management teams to the islands |  | Quaternaire Portugal, SA
Trips for project coordination, management and administrative teams - cost-of-living allowance | days | 169 | 69.19 | 11693.11 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Use of computer equipment by the administrative team | months | 30 | 96.75 | 2902.5 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
Acquisition of new IT equipment for the coordination team | computer | 2 | 2500 | 5000 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | Acquisition of two laptops |  | Quaternaire Portugal, SA
Total 1.1: |  |  |  | 316524.47
Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR)
Search and development of the list of information to be collected | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Valor médio /homem / dia para uma equipa de quadros superiores que integra Administrador, Consultor-coordenador e consultor / Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Draw up of requests for information, through direct contact with each of the BRmanagers | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of the information received | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Loading into the project database | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 28 | 2 | 56 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.2: |  |  |  | 4736
Output / Activity 2 - Survey of existing BR action plans, objectives and priorities.
Summary of the various management documents existing in the BRs (action plans, management reports, etc.) identifying, namely, priorities and projects in progress or planned to be validated | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Fieldwork and meetings with BR managers on the mainland | trip | 18 | 150 | 2700 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Fieldwork and Meetings with BR managers in the Islands | trip | 12 | 400 | 4800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 30 | 69.19 | 2075.7 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Updating the objectives and priority projects of each BR | days | 15 | 180 | 2700 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Utilização de equipamentos informáticos/ Use of computer equipment | days | 55 | 2 | 110 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.3: |  |  |  | 14185.7
Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks
Identification of the Strategic Reference Framework | days | 7 | 200 | 1400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of information | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of the objectives, indicators and goals of the different documents with an impact on PR | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of critical aspects | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of the governance framework | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Formalisation of the Geostrategic Framework Report | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 44 | 2 | 88 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
Total 1.4: |  |  |  | 8088
Output / Activity 4 - History of BR
Production and revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); historical and heritage research; preparation, production and editing of contents |  | Universidade Nova de Lisboa
Database | numeric | 1 | 6150 | 6150 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for database development |  | Universidade Nova de Lisboa
Research Trips | days | 5 | 1580 | 7900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips of research scholarship holders (data collection) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
Total 1.5: |  |  |  | 27308
Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the data management plan |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.6: |  |  |  | 2392
Output / Activity 6 - Auscultation / Perception and identification of heritage
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); data/information survey |  | Universidade Nova de Lisboa
Research Trips | days | 6 | 1580 | 9480 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip of research scholarship holder (data survey) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.7: |  |  |  | 11872
Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR
Benchmarking analysis of existing international and national SDPs | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Contact with international partners | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Identification of frameworks, contents and typologies of proposals, development methodologies, ways of participation and follow-up, management and execution model | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Selection of best practices | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Integration of critical aspects of the SRF (Strategic Reference Framework) | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Design of the structure, contents and methodologies for SDPs | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Formalisation of the Report Structure of the SDPs to be submitted for approval (Activity 9) | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Review and edition of the final version of the SDPs Structure Report (after approval - Activity 9) | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 42 | 2 | 84 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.8: |  |  |  | 8124
Output / Activity 8 - Development of the participatory planning methodology for the SDP
Identification of the practices and guidelines established in the Lima Plan | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of entities, agents, experts and others to be involved | days | 3 | 200 | 600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Cross-check with Activity 7 results to identify the best practices already being applied | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of weaknesses | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Proposals for new participatory practices | days | 4 | 180 | 720 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Establishment of the Supervising Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Establishment of the approach methodology | days | 5 | 200 | 1000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Programming of the different participation periods and their associated methods | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the Participatory Planning Methodology Report | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 31 | 2 | 62 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
Total 1.9: |  |  |  | 5842
Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP
Organisation of the presentation session of the SDPs Structure Report | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Presentation of the SDPs Structure Report to the Supervisor Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of contributions received | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 10 | 2 | 20 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.10: |  |  |  | 1860
Output / Activity 10 - Digital Infrastructure - distributed management model
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the digital infrastructure management model |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.11: |  |  |  | 2392
Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website
Website development and programming | numeric | 1 | 64575 | 64575 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for development and programming of website/digital platform of the Biosphere Reserves with custom application logic (integration with databases; virtual store; APIs for integration with services/external entities) |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.12: |  |  |  | 64575
Output / Activity 12 - Digital infrastructure - Indicators management dashboard
Business Intelligence Platform | numeric | 1 | 24600 | 24600 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for business intelligence platform development |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.13: |  |  |  | 24600
Output / Activity 13 - Digital Infrastructure - Research Data Catalog
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of the data catalogue |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.14: |  |  |  | 2392
Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); preparation and production of content based on the historical research developed |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.15: |  |  |  | 13258
Output / Activity 15 - Mapping the BR ecosystem diversity
Computer equipment - high performance desktop computer | computer | 1 | 2136 | 2136 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €3,000, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Computer equipment - high performance desktop computer | laptop | 1 | 1780 | 1780 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €2,500, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Computer equipment - External storage disks | disk | 4 | 178 | 712 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | This equipment will have a total cost of €1,000, being amortised in 71.20% throughout the project. The equipment will be used in all activities developed by the University of Coimbra |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.89 | 5160.1745 | 9752.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,89 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.81 | 5160.1745 | 4179.74 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,81 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.5 | 1331.74 | 3329.35 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Travel from Norway to Coimbra to start project activities, and outline joint strategies | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
0
Total 1.16: |  |  |  | 28440.55
Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.47 | 5160.1745 | 7585.46 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,47 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.63 | 5160.1745 | 3250.91 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,63 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.9 | 1331.74 | 3862.05 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
0
Total 1.17: |  |  |  | 17264.15
Output / Activity 17 - Analysis of the dynamics of the socio-economic sector
Statistical analysis and desk research and preparation of information collection tools | days | 10 | 182 | 1820 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Carry out of interviews and online surveys | days | 15 | 182 | 2730 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant and base consultant |  | Quaternaire Portugal, SA
Management of online surveys | days | 10 | 79.45 | 794.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management that includes s a base consultant |  | Quaternaire Portugal, SA
Trips for interviews - cost-of-living allowance | days | 20 | 69.19 | 1383.8 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Trips for interviews - travels in mainland | trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Trips for interviews - travels in the Islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Drawing up of final document | days | 5 | 182 | 910 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 40 | 2 | 80 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.18: |  |  |  | 10618.3
Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR
Identification of local players to explore territorial resources (analysis and institutional contacts) | months | 1.5 | 3400.925 | 5101.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Identification of local players to explore resources of territories (through desk research, compilation of information and direct contacts) | months | 6 | 2245.19 | 13471.14 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Direct contacts for information collection | mission | 2 | 476.76 | 953.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
0
0
0
Total 1.19: |  |  |  | 19526.05
Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development
Identification of good practices in R&TD, innovation and entrepreneurship aligned with sustainable development (literature review and institutional contacts) | months | 1.5 | 3400.925 | 5101.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Identification of good practices in R&TD, innovation and entrepreneurship aligned with sustainable development (direct contacts, information compilation and content production for local teams) | months | 6 | 2245.19 | 13471.14 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 2 | 476.76 | 953.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
0
0
0
Total 1.20: |  |  |  | 19526.05
Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability
Preparation of the base document identifying priorities in each BR as a result of Activity 3 | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of focus action groups | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Listening to local players and agents of BRs in the mainland | trip | 15 | 150 | 2250 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Listening to local players and agents of BRs in the islands | trip | 10 | 400 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of Focus Group | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of contributions and results of participatory sessions | days | 15 | 180 | 2700 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of technical content with identification of Priorities for each BR | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 63 | 2 | 126 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.21: |  |  |  | 14945.75
Output / Activity 21 - Selection of key ES for the sustainable development of BR
Travel to the BR of Nordhordland | mission | 1 | 2725 | 2725 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel to design the application of participatory mapping methodology and social and analysis of social and socio-ecological network with partners from Norway (5 days x 2pax) |  | Universidade de Coimbra
Trips to BRs for ES selection | mission | 11 | 1856 | 20416 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for questionnaires, interviews and focus groups (3 days in each BR x 3 pax) |  | Universidade de Coimbra
Miscellaneous consumables (supplies) to support activities | unit | 11 | 100 | 1100 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Consumables necessary for the implementation of the participatory methodology for selection of ES in each of the 11 BRs |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.54 | 5160.1745 | 7946.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,54 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.66 | 5160.1745 | 3405.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,66 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Travel from Nordhordland to Portugal | mission | 1 | 700 | 700 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs from Norway to Portugal |  | Nordhordland Utviklingsselskap IKS
Trips to selected BRs | mission | 4 | 586.38 | 2345.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 4 visits for participation in the participatory methodology (1 days in each BR x 1 pax) |  | Nordhordland Utviklingsselskap IKS
Total 1.22: |  |  |  | 53322.93
Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.54 | 5160.1745 | 7946.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,54 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.66 | 5160.1745 | 3405.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,66 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3 | 1331.74 | 3995.22 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
Total 1.23: |  |  |  | 21669.32
Output / Activity 23 - ES condition / status assessment
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.68 | 5160.1745 | 8669.09 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,68 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.72 | 5160.1745 | 3715.33 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,72 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3 | 1331.74 | 3995.22 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.75 | 1926.15 | 3370.76 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.75 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
0
Total 1.24: |  |  |  | 22316.13
Output / Activity 24 - ES valuation proposal (add value)
Trips to BRs for the definition of strategies of Valorisation and Valuation of ES | mission | 11 | 1238 | 13618 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for questionnaires, interviews and focus groups (3 days in each BR x 2 pax) |  | Universidade de Coimbra
Miscellaneous consumables (supplies) to support activities | unit | 11 | 100 | 1100 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Consumables necessary for the implementation of participatory methodology for valuing and valuing ES in each of the 11 BRs |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.61 | 5160.1745 | 8307.88 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,61 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.69 | 5160.1745 | 3560.52 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,69 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.8 | 1331.74 | 2397.13 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.8 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Travel from Nordhordland to Portugal | mission | 1 | 700 | 700 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs from Norway to Portugal |  | Nordhordland Utviklingsselskap IKS
Trips to selected BRs | mission | 4 | 586.38 | 2345.52 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 4 visits for participation in the participatory methodology (1 days in each BR x 1 pax) |  | Nordhordland Utviklingsselskap IKS
0
0
Total 1.25: |  |  |  | 40426.78
Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action
Consultancy in the area of valuation of ES | unit | 11 | 900 | 9900 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Specialised consultancy in the field of valuation of ES and methodologies and ways of calculating economic and natural value (2 consultants x 11 months consulting) |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 8.85 | 1926.15 | 17046.43 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 8.85 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.26: |  |  |  | 26946.43
Output / Activity 26 - Mapping BR ES
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 2.03 | 5160.1745 | 10475.16 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 2.03 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.87 | 5160.1745 | 4489.35 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,87 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 2.9 | 1331.74 | 3862.05 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.65 | 1926.15 | 3178.15 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.65 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
0
0
0
0
0
Total 1.27: |  |  |  | 30402.44
Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.98 | 5160.1745 | 5056.97 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,98 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.42 | 5160.1745 | 2167.27 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,42 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.85 | 1926.15 | 3563.38 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.85 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.28: |  |  |  | 10787.62
Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.75 | 5160.1745 | 9030.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,75 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.75 | 5160.1745 | 3870.13 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,75 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44c |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 3.2 | 1331.74 | 4261.57 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 3.2 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 2.05 | 1926.15 | 3948.61 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.05 months, being hired for 24 months on an exclusive basis, and with a total cost of €42375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Travel from Norway to Coimbra to collaborate in the modelling of ES | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
0
0
0
Total 1.29: |  |  |  | 27661.35
Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action
Trip to BR for selection of ES to mitigate and adapt to climate change | mission | 11 | 1238 | 13618 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 11 visits for the application of the participatory methodology (3 days in each BR x 2 pax). These trips will also serve for the development of activity 73 (Awareness-raising Actions about ES) |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.19 | 5160.1745 | 6140.61 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1.19 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.51 | 5160.1745 | 2631.69 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,51 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.7 | 1331.74 | 2263.96 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Research Scholarship - Post-doctoral | person/month | 1.95 | 1926.15 | 3755.99 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.95 months, being hired for 24 months on an exclusive basis, and with a total cost of €42,375.36 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
0
0
0
0
0
Total 1.30: |  |  |  | 30975.98
Output / Activity 30 - ES Sustainable Management Manual for BR
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0.36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.31: |  |  |  | 8722.52
Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR
Development and combination of the different contributions of the team and participatory sessions for the contents of the SDPs | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the 11 SDPs | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of participatory discussion sessions | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Islands | trip | 8 | 400 | 3200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 20 | 69.19 | 1383.8 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of participatory discussion sessions | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation and systematisation of contributions and results of participatory sessions | days | 3 | 180 | 540 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 71 | 2 | 142 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.32: |  |  |  | 12285.8
Output / Activity 32 - SDP public presentations and discussions
Organisation of public discussion sessions | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Mainland | trip | 10 | 150 | 1500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Participatory discussion session in the BRs of the Islands | trip | 8 | 400 | 3200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 16 | 69.19 | 1107.04 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Participation and promotion of public discussion sessions | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Compilation, systematisation and consideration of contributions and results of the public discussion period | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Validation of the consideration and formalisation of the respective report | days | 5 | 180 | 900 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 45 | 2 | 90 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.33: |  |  |  | 11117.04
Output / Activity 33 - Revision and editing of the final versions of the SDP
Modification of the SDPs according to the consideration of public participation and the follow-up and evaluation of pilot actions | days | 22 | 180 | 3960 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Non-technical summary of SDPs highlighting strategy success factors | days | 10 | 200 | 2000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 32 | 2 | 64 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.34: |  |  |  | 6024
Output / Activity 34 - Selection of 11 pilot actions
Definition of a matrix of selection criteria for pilot actions | days | 1 | 180 | 180 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Reflection and discussion among partners on the impact on BR actions | days | 1 | 200 | 200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Proposal of pilot actions by BR | days | 1 | 2 | 2 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.35: |  |  |  | 382
Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action
Survey and initial recognition of BRs | days | 23 | 121.86 | 2802.78 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Development of Tourist Guidebooks | days | 33 | 121.86 | 4021.38 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Technical work in BRs - cost-of-living allowance | days | 40 | 69.19 | 2767.6 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Technical work in BRs - trips on the Mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Technical work in BRs - trips to the Islands | trip | 10 | 400 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical development of tourist guidebooks (research, organisation, writing) | days | 45 | 121.86 | 5483.7 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant. In conjunction with Communication actions (fan trips and participation in tourism fairs) |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.36: |  |  |  | 20875.46
Output / Activity 36 - Memories and identities - systematic record of memories
Training actions | days | 11 | 1230 | 13530 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | 11 training actions (2 days in each BR x 3 pax) |  | Universidade Nova de Lisboa
Presentation trips | days | 11 | 1590 | 17490 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for presentation of the project in each of the 11 reserves (3pax per session) |  | Universidade Nova de Lisboa
Training trips | days | 11 | 1590 | 17490 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips to training sessions in each of the 11 reserves (3 PAX per session) |  | Universidade Nova de Lisboa
Interview trips | days | 11 | 1270 | 13970 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips to collect memories in each of the 11 reserves (5 days per BR; 2 PAX) |  | Universidade Nova de Lisboa
Validation of interviews trips | days | 11 | 425 | 4675 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for validation of interviews in each of 11 reserves (2 days per BR; 1 PAX) |  | Universidade Nova de Lisboa
Audiovisual recording equipment | numeric | 3 | 2510 | 7530 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Interview storage equipment | numeric | 6 | 150 | 900 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Audiovisual editing software | numeric | 1 | 999.9 | 999.9 | Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 |  |  | Universidade Nova de Lisboa
Technical Editing of Content | hours | 660 | 18.45 | 12177 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
App for recording memories | numeric | 1 | 18450 | 18450 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Acquisition of services for the development of an app for registration and management of intangible cultural heritage (memories) |  | Universidade Nova de Lisboa
HR (researchers) | numeric | 1 | 9568 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); preparation and carry out of interviews; analysis of the contents of the interviews |  | Universidade Nova de Lisboa
Total 1.37: |  |  |  | 116779.9
Output / Activity 37 - Creation of memory and community spaces - pilot action
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the build-up of memory spaces in pilot reserve |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.38: |  |  |  | 6082
Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action
Design, development of the concept and model of the store network for the Biosphere Reserves | days | 30 | 182 | 5460 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 25 | 2 | 50 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
0
Total 1.39: |  |  |  | 5510
Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks
Identifying the different indicator systems used in BR and the best practices implemented | days | 20 | 180 | 3600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Contacts with international partners | days | 6 | 200 | 1200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Three case studies | days | 15 | 180 | 2700 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 84 | 2 | 168 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.40: |  |  |  | 7668
Output / Activity 40 - Architecture of SDP indicators and monitoring system
Definition of the system of indicators for the national network and for each BR | days | 15 | 200 | 3000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Identification of the sources of information to be mobilised | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Definition of data collection locations and their frequency | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Specification of techniques and equipment for data collection | days | 8 | 180 | 1440 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Especificação de critérios de avaliação/ Specification of evaluation criteria | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Identification of entities involved for the provision of information and active participation in the collection and input of the monitoring plan | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Development of datasheets by indicator | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Formalisation of the monitoring plan/indicator system | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 70 | 2 | 140 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.41: |  |  |  | 13040
Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system
Organisation of the presentation session of monitoring plans/indicator system | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Submission of monitoring plans/indicator system to the Supervising Committee | days | 2 | 200 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Collection and systematisation of contributions received | days | 6 | 180 | 1080 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Development of the final version of monitoring plans/indicator system | days | 10 | 180 | 1800 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 24 | 2 | 48 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.42: |  |  |  | 4408
Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System
Design of the training programme | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 2 | 150 | 300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 6 | 69.19 | 415.14 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 3 | 220 | 660 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 23 | 2 | 46 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.43: |  |  |  | 8021.14
Output / Activity 43 - Citizen Science for sustainable BR - pilot action
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the promotion of citizen science activities with the Reserves, and in collaboration with the National Network of Citizen Science |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.44: |  |  |  | 2392
Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves
Architecture and selection of representative indicators to be integrated in the barometer from the perspective of management and communication | days | 10 | 200 | 2000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Validation of the proposal with the Supervising Committee | days | 3 | 200 | 600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Generation of reports | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Generation of graphic elements for communication and training actions | days | 7 | 180 | 1260 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 27 | 2 | 54 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.45: |  |  |  | 5174
Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves
Development of technical design | days | 30 | 121.86 | 3655.8 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Benchmarking analysis | days | 10 | 121.86 | 1218.6 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Training actions in the scope of certification and good practices in Sustainable Tourism: face-to-face (practical component) and online (general content) | days | 44 | 121.86 | 5361.84 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Quaternaire Portugal, SA
Technical work with BR managers - cost-of-living allowance | days | 22 | 69.19 | 1522.18 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Technical work with BR managers - trips on the Mainland | trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the mainland |  | Quaternaire Portugal, SA
Technical work with BR managers - trips to the Islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the islands |  | Quaternaire Portugal, SA
Design, organisation and drafting of the Sustainable Tourism Guidebook | days | 15 | 121.86 | 1827.9 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Quaternaire Portugal, SA
0
0
0
Total 1.46: |  |  |  | 16486.32
Output / Activity 46 - Assessment of training needs that will support the training planing
Design of the methodological strategy of diagnosis | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Collection of diagnostic support information | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of the diagnostic of training needs | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of Training Plans for the 11 Reserves | days | 22 | 220 | 4840 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the mainland |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for technical team on the islands |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | cost-of-living allowances | 33 | 69.19 | 2283.27 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Use of computer equipment | days | 87 | 2 | 174 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
Total 1.47: |  |  |  | 23747.27
Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents.
Design of the training programme | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 1 | 400 | 400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for trainees from the islands |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 33 | 69.19 | 2283.27 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 3 | 220 | 660 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes an Administrator, Consultant-coordinator and consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 28 | 2 | 56 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.48: |  |  |  | 11349.27
Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP.
Design of the training programme | days | 10 | 220 | 2200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Configuration of the online platform and development of educational resources for the implementation of training | days | 20 | 220 | 4400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Monitoring | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Travel costs for trainees from the mainland |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | trip | 1 | 400 | 400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for trainees from the islands |  | Quaternaire Portugal, SA
Carrying out of the face-to-face training component | cost-of-living allowances | 44 | 69.19 | 3044.36 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trainee cost-of-living allowances |  | Quaternaire Portugal, SA
Monitoring and evaluation of training | days | 5 | 220 | 1100 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Use of computer equipment | days | 35 | 2 | 70 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
Total 1.49: |  |  |  | 14764.36
Output / Activity 49 - Training associated with the implementation of pilot actions
Analysis and monitoring of pilot actions and identification of new skills | days | 15 | 220 | 3300 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Development of the analysis report and development of a plan for the dissemination of new competences related to pilot actions | days | 22 | 220 | 4840 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Actions to disseminate new competencies | days | 30 | 220 | 6600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant-coordinator and a consultant |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 9 | 150 | 1350 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs for the technical team on the mainland |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | trip | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trip costs of the technical team on the islands |  | Quaternaire Portugal, SA
Activities supporting information collection and consultation with relevant interlocutors | cost-of-living allowances | 30 | 69.19 | 2075.7 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance for technical team |  | Quaternaire Portugal, SA
Use of computer equipment | days | 67 | 2 | 134 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
Total 1.50: |  |  |  | 19099.7
Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities
Design and coordination of the training of local teams | months | 4 | 3400.925 | 13603.7 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Support of local BR teams, during and after training, to carry out activities to support economic initiative, search for partnerships (companies and other stakeholders) and financing, both public and private. | months | 9 | 2245.19 | 20206.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Carrying out online training | months | 1 | 2245.19 | 2245.19 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 trainers |  | Instituto Pedro Nunes, AIDCT
Creation of training materials | numeric | 1 | 750 | 750 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | training materials |  | Instituto Pedro Nunes, AIDCT
Zoom License | months | 12 | 13.99 | 167.88 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Zoom License |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 4 | 476.76 | 1907.04 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
Total 1.51: |  |  |  | 38880.52
Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 1.05 | 5160.1745 | 5418.18 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 1,05 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.45 | 5160.1745 | 2322.08 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,45 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
0
0
0
0
0
0
0
Total 1.52: |  |  |  | 16137.99
Output / Activity 52 - Technical workshop on ecosystem services
Printing material and consumables | person | 60 | 10 | 600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Printing of supporting material, including technical documents, and consumables (notebooks, pens, folders, etc.) to support for the workshop |  | Universidade de Coimbra
Catering service (including lunch and 2 coffee-breaks) | person | 60 | 25 | 1500 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Catering service for the workshop, including lunch and 2 coffee-breaks for 50 people |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 1.9 | 1331.74 | 2530.31 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 1.9 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
Inger Måren's wage imputation | person/month | 0.27273 | 9407.6667 | 2565.73 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | These human resources costs represent a percentage of 10% dedication over the 30 months of the project, with a total cost of €28,223 |  | University of Bergen
Nordhordland Biosphere Reserve Technician | person/month | 0.9 | 6480 | 5832 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | This human resource will provide support in the development of the task, and has a monthly cost of €29,160 |  | Nordhordland Utviklingsselskap IKS
Trips for active participation in the workshop | mission | 1 | 1450 | 1450 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost includes travel from Norway to Portugal, 8 days of cost-of-living allowance and 7 nights stay for 1 person, who will participate in the organisation of the workshop |  | Nordhordland Utviklingsselskap IKS
Travel from Norway to Coimbra to participate in the organisation of the workshop | mission | 1 | 3985 | 3985 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | This mission includes the trip from Norway to Portugal, and 2 weeks of accommodation and cost-of-living allowance for 1 person |  | University of Bergen
0
0
Total 1.53: |  |  |  | 24655.25
Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action
Design and coordination of the training of local entrepreneurship projects | months | 4.5 | 3400.925 | 15304.16 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (1 Coordinator at 50% of the time) |  | Instituto Pedro Nunes, AIDCT
Entrepreneurs' support, during the post-training, to explore the commercial validity of their project, to seek partnerships and sources of funding | months | 9 | 2245.19 | 20206.71 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human Resources (a technician at 100% of the time) |  | Instituto Pedro Nunes, AIDCT
Carrying out online training | months | 5 | 2245.19 | 11225.95 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 trainers |  | Instituto Pedro Nunes, AIDCT
Creation of training materials | numeric | 1 | 3500 | 3500 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Training materials |  | Instituto Pedro Nunes, AIDCT
Online workshops and trainings | months | 24 | 13.99 | 335.76 | Costs of consumables and supplies - Reg. Art. 8.3.1.e | Zoom License |  | Instituto Pedro Nunes, AIDCT
Trips and stays | mission | 6 | 715.14 | 4290.84 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value per mission that includes trip costs and cost-of-living allowance |  | Instituto Pedro Nunes, AIDCT
0
0
0
0
Total 1.54: |  |  |  | 54863.42
Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries
Follow-up of the Visits programme | days | 5 | 121.86 | 609.3 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Participation in the Visits programme | days | 4 | 1250 | 5000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Icelandic National Commission for UNESCO
Carrying out visits - trips on the mainland | trip | 12 | 150 | 1800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips on the mainland |  | Quaternaire Portugal, SA
Carrying out visits - trips to the islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips on the islands |  | Quaternaire Portugal, SA
0
0
0
0
0
0
Total 1.55: |  |  |  | 9409.3
Output / Activity 55 - Final project seminar
Follow-up of the organisation of the final Seminary | days | 15 | 121.86 | 1827.9 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes an Expert consultant |  | Quaternaire Portugal, SA
Participation in the final Seminar | days | 4 | 1250 | 5000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day |  | Icelandic National Commission for UNESCO
Organisation and production of the final seminar | event | 1 | 30000 | 30000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | hiring a company specialised in events |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
Total 1.56: |  |  |  | 36827.9
Output / Activity 56 - Marketing Strategy Development
Coordination of the development of the marketing strategy | hour | 70 | 112.5 | 7875 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development of marketing strategy | hour | 25 | 40 | 1000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for the design and development of the marketing strategy | hour | 80 | 5 | 400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 44 | 69.19 | 3044.36 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 22 | 150 | 3300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
Total 1.57: |  |  |  | 17219.36
Output / Activity 57 - Communication Plan Design
Coordination of the development of the communication plan | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development of communication plan | hour | 50 | 80 | 4000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services - 2 consultants |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work on the development of the communication plan | hour | 110 | 5 | 550 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 30 | 150 | 4500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
Total 1.58: |  |  |  | 17442.25
Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook)
Coordination of development | hour | 70 | 112.5 | 7875 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 80 | 80 | 6400 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 280 | 5 | 1400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 5 | 69.19 | 345.95 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 5 | 150 | 750 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.59: |  |  |  | 16770.95
Output / Activity 59 - Generic Creative Development
Coordination of development | hour | 60 | 112.5 | 6750 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 120 | 80 | 9600 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 130 | 5 | 650 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 5 | 69.19 | 345.95 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 5 | 150 | 750 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.60: |  |  |  | 18095.95
Output / Activity 60 - Creative development of digital communication
Coordination of development | hour | 50 | 112.5 | 5625 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Technician work for development | hour | 80 | 80 | 6400 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 90 | 5 | 450 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 2 | 69.19 | 138.38 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 2 | 150 | 300 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
Total 1.61: |  |  |  | 12913.38
Output / Activity 61 - Productions and promotional materials - Offline
Coordination of development | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 125 | 45 | 5625 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 50 | 5 | 250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Promotion materials (offline) | Set of communication items to be produced within the scope of the activity | 1 | 78500 | 78500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.62: |  |  |  | 89437.5
Output / Activity 62 - Productions and promotional materials - Online
Coordination of development | hour | 50 | 112.5 | 5625 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 125 | 45 | 5625 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Promotion materials (on line) | Set of communication items to be produced within the scope of the activity | 1 | 52000 | 52000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
0
Total 1.63: |  |  |  | 63250
Output / Activity 63 - Productions and promotional materials - Audiovisual materials
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 75 | 45 | 3375 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 40 | 5 | 200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Audiovisual Materials | Set of communication items to be produced within the scope of the activity | 1 | 13500 | 13500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.64: |  |  |  | 18762.5
Output / Activity 64 - Brand Activations
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 225 | 45 | 10125 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 30 | 5 | 150 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 25 | 69.19 | 1729.75 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 15 | 150 | 2250 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missões / missions | 4 | 400 | 1600 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
Brand Activations | Set of communication items to be produced within the scope of the activity | 1 | 17500 | 17500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
Total 1.65: |  |  |  | 35042.25
Output / Activity 65 - Public Relations
Coordination of development | hour | 45 | 112.5 | 5062.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 150 | 25 | 3750 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - cost-of-living allowance | days | 10 | 69.19 | 691.9 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Cost-of-living allowance of €69,19 per day/person |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 10 | 150 | 1500 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for mainland - €150 |  | PC&A - Consultores de Marketing Estratégico, Lda
Trips - travels | missions | 2 | 400 | 800 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value for Islands - €400 |  | PC&A - Consultores de Marketing Estratégico, Lda
Public relations | months | 20 | 825 | 16500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of acquired services is only an estimation (fees/month) |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
Total 1.66: |  |  |  | 28679.4
Output / Activity 66 - Media Strategy and Planning
Coordination of development | hour | 15 | 112.5 | 1687.5 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
0
0
0
Total 1.67: |  |  |  | 1687.5
Output / Activity 67 - Media Strategy and Planning - Press
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 50 | 25 | 1250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Press | advertisements and other advertising media | 1 | 13300 | 13300 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.68: |  |  |  | 17175
Output / Activity 68 - Media Strategy and Planning - Radio
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Valor/hora médio de 2019/ Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 50 | 25 | 1250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 50 | 5 | 250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Digital | advertisements and other advertising media | 1 | 13500 | 13500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.69: |  |  |  | 17250
Output / Activity 69 - Media Strategy and Planning - Digital
Coordination of development | hour | 20 | 112.5 | 2250 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/hour 2019 |  | PC&A - Consultores de Marketing Estratégico, Lda
Follow-up of the activity of the process | hour | 250 | 25 | 6250 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Contract for the provision of services |  | PC&A - Consultores de Marketing Estratégico, Lda
Technical support for work | hour | 75 | 5 | 375 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Administrative technicians -% of time allocated to the project |  | PC&A - Consultores de Marketing Estratégico, Lda
Media Strategy and Planning - Digital | advertisements and other advertising media | 1 | 43500 | 43500 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | The number of purchased services is only an estimation |  | PC&A - Consultores de Marketing Estratégico, Lda
0
0
0
0
0
0
Total 1.70: |  |  |  | 52375
Output / Activity 70 - Culture and Education Agenda
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the development of a cultural and educational agenda |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
0
Total 1.71: |  |  |  | 2392
Output / Activity 71 - Development of Awareness Plan for different audiences
Technical Development | days | 10 | 122.83 | 1228.3 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/day for a senior management team that includes a Consultant |  | Quaternaire Portugal, SA
0
0
0
0
0
0
0
0
0
Total 1.72: |  |  |  | 1228.3
Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners
Organisation of presentation sessions | days | 2 | 180 | 360 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Presentation discussion session in the BRs of the Mainland | trip | 8 | 150 | 1200 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Presentation discussion session in the BRs of the Islands | deslocação / trip | 6 | 400 | 2400 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Technical support to promoters of applications - cost-of-living allowance | days | 14 | 69.19 | 968.66 | Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Use of computer equipment | days | 16 | 2 | 32 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
0
Total 1.73: |  |  |  | 4960.66
Output / Activity 73 - ES awareness actions
Hiring of Assistant Researcher DL 124/99 - 70% | person/month | 0.84 | 5160.1745 | 4334.55 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,84 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €99 333,36 |  | Universidade de Coimbra
Hiring of Assistant Researcher DL 124/99 - 30% | person/month | 0.36 | 5160.1745 | 1857.66 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The researcher will be allocated to this activity 0,36 months, being hired by the total of the project (i.e. 30 months), and having a total cost of €42 571,44 |  | Universidade de Coimbra
Research Scholarship - Master | person/month | 0.8 | 1331.74 | 1065.39 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | The scholarship holder will be allocated to this activity for 2.5 months, being hired for 30 months on an exclusive basis, and with a total cost of €36,622.76 |  | Universidade de Coimbra
0
0
0
0
0
0
0
0
Total 1.74: |  |  |  | 7257.6
Output / Activity 74 - Planning of the National Biosphere Olympics
Olympiads planning: Development of regulations, preparation of tests, planning of logistics and scientific part, including formation of commissions | months | 2 | 500 | 1000 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human resources, staff of the Order of Biologists |  | Ordem dos Biólogos
Human Resources | months | 3 | 1193.89 | 3581.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Hiring a Master for logistic support |  | Ordem dos Biólogos
0
0
0
0
0
0
0
0
Total 1.75: |  |  |  | 4581.67
Output / Activity 75 - Communication and dissemination of the BR Olympics
Promotion process for the Olympiad, including production and distribution of posters and preparation of the dedicated website for registration and information | months | 1 | 500 | 500 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Human resources, staff of the Order of Biologists |  | Ordem dos Biólogos
Acquisition of services: material for tests, communications | months | 5 | 800 | 4000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
0
0
0
0
0
0
0
0
Total 1.76: |  |  |  | 4500
Output / Activity 76 - BR Olympics
Recursos Humanos/ Human Resources | months | 3 | 1193.89 | 3581.67 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Hiring a Master for logistic support |  | Ordem dos Biólogos
Trips for students and organisation staff for the final | people to transport | 50 | 80 | 4000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b |  |  | Ordem dos Biólogos
Accommodation for participants | rooms/overnight stays | 100 | 50 | 5000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | Accommodation hiring |  | Ordem dos Biólogos
Food - meals during the final test | meals | 400 | 15 | 6000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
Trophies and prises for the winners | trophies | 50 | 60 | 3000 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Ordem dos Biólogos
Merchandising - T-shirts, vests, backpacks, banners, roll-ups, flyers | articles | 200 | 20 | 4000 | Costs of consumables and supplies - Reg. Art. 8.3.1.e |  |  | Ordem dos Biólogos
Jury support | members of the jury | 8 | 375 | 3000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b |  |  | Ordem dos Biólogos
0
0
0
Total 1.77: |  |  |  | 28581.67
Output / Activity 77 - Design and organization of Biosphere Reserve Festivals
Design and structuring of Festivals | days | 40 | 130 | 5200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organisation of Festivals | days | 40 | 130 | 5200 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Average value/man/ day for a senior management team that includes Consultant-Coordinator, consultant and base consultant |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - cost-of-living allowance | days | 22 | 69.19 | 1522.18 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | The cost-of-living allowance is considered according to the official table |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - trips in mainland | deslocação / trip | 6 | 150 | 900 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs within the Mainland |  | Quaternaire Portugal, SA
Organise with each BR the input and update scheme of the agenda - trips to the islands | trip | 5 | 400 | 2000 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Average value of trips to BRs in the Islands |  | Quaternaire Portugal, SA
Use of computer equipment | days | 30 | 2 | 60 | Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | Amortisation of computers and printers |  | Quaternaire Portugal, SA
0
0
0
0
Total 1.78: |  |  |  | 14882.18
Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB
BioKeepers activity management (HR) | months | 12 | 1800 | 21600 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Contract Project management; Relationship with schools; BioKeepers |  | KEEP - Knowledge for Peace, People and the Planet, Association
Presentation trips | days | 11 | 430 | 4730 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | Trips for presentation and awareness-raising of communities about the BioKeepers activity |  | KEEP - Knowledge for Peace, People and the Planet, Association
0
0
0
0
0
0
0
0
Total 1.79: |  |  |  | 26330
Output / Activity 79 - Atlas of Portuguese Biosphere reserves
HR (researchers) | numeric | 2 | 4784 | 9568 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 2 Research Scholarship holders (in the value of master); research for and preparation of contents for the development of an Atlas of Biosphere Reserves |  | Universidade Nova de Lisboa
Revision of texts | numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.80: |  |  |  | 13258
Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension
Management of Activity of Extension of Knowledge (HR) | months | 18 | 1800 | 32400 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | Contract Project management; Relationship with schools and local entitie |  | KEEP - Knowledge for Peace, People and the Planet, Association
Trips Coordination | days | 11 | 1310 | 14410 | Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 14 days of face-to-face-coordination for each reserve |  | KEEP - Knowledge for Peace, People and the Planet, Association
0
0
0
0
0
0
0
0
Total 1.81: |  |  |  | 46810
Output / Activity 81 - Itinerant exhibition
HR (researchers) | numeric | 1 | 2392 | 2392 | Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 1 Research Scholarship holder (in the value of master); support for the organisation and management of contents for the travelling exhibition |  | Universidade Nova de Lisboa
Revision of texts | numérico / numeric | 1 | 3690 | 3690 | Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f |  |  | Universidade Nova de Lisboa
0
0
0
0
0
0
0
0
Total 1.82: |  |  |  | 6082
Total 1: |  |  |  | 1944647.28
2. INDIRECT COSTS*
Total 2: |  |  |  | 254019.18
TOTAL Project COST (1 + 2): |  |  |  | 2198666.46
Total project management cost (€): |  |  |  | 316524.47
Total output related cost (€): |  |  |  | 1628122.81
Output / Activity Budget Heading | Management cost | Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR) | Output / Activity 2 - Survey of existing BR action plans, objectives and priorities. | Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks | Output / Activity 4 - History of BR | Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access | Output / Activity 6 - Auscultation / Perception and identification of heritage | Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR | Output / Activity 8 - Development of the participatory planning methodology for the SDP | Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP | Output / Activity 10 - Digital Infrastructure - distributed management model | Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website | Output / Activity 12 - Digital infrastructure - Indicators management dashboard | Output / Activity 13 - Digital Infrastructure - Research Data Catalog | Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves | Output / Activity 15 - Mapping the BR ecosystem diversity | Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems | Output / Activity 17 - Analysis of the dynamics of the socio-economic sector | Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR | Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development | Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability | Output / Activity 21 - Selection of key ES for the sustainable development of BR | Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES | Output / Activity 23 - ES condition / status assessment | Output / Activity 24 - ES valuation proposal (add value) | Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action | Output / Activity 26 - Mapping BR ES | Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization | Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures | Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action | Output / Activity 30 - ES Sustainable Management Manual for BR | Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR | Output / Activity 32 - SDP public presentations and discussions | Output / Activity 33 - Revision and editing of the final versions of the SDP | Output / Activity 34 - Selection of 11 pilot actions | Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action | Output / Activity 36 - Memories and identities - systematic record of memories | Output / Activity 37 - Creation of memory and community spaces - pilot action | Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action | Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks | Output / Activity 40 - Architecture of SDP indicators and monitoring system | Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system | Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System | Output / Activity 43 - Citizen Science for sustainable BR - pilot action | Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves | Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves | Output / Activity 46 - Assessment of training needs that will support the training planing | Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents. | Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP. | Output / Activity 49 - Training associated with the implementation of pilot actions | Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities | Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans | Output / Activity 52 - Technical workshop on ecosystem services | Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action | Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries | Output / Activity 55 - Final project seminar | Output / Activity 56 - Marketing Strategy Development | Output / Activity 57 - Communication Plan Design | Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook) | Output / Activity 59 - Generic Creative Development | Output / Activity 60 - Creative development of digital communication | Output / Activity 61 - Productions and promotional materials - Offline | Output / Activity 62 - Productions and promotional materials - Online | Output / Activity 63 - Productions and promotional materials - Audiovisual materials | Output / Activity 64 - Brand Activations | Output / Activity 65 - Public Relations | Output / Activity 66 - Media Strategy and Planning | Output / Activity 67 - Media Strategy and Planning - Press | Output / Activity 68 - Media Strategy and Planning - Radio | Output / Activity 69 - Media Strategy and Planning - Digital | Output / Activity 70 - Culture and Education Agenda | Output / Activity 71 - Development of Awareness Plan for different audiences | Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners | Output / Activity 73 - ES awareness actions | Output / Activity 74 - Planning of the National Biosphere Olympics | Output / Activity 75 - Communication and dissemination of the BR Olympics | Output / Activity 76 - BR Olympics | Output / Activity 77 - Design and organization of Biosphere Reserve Festivals | Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB | Output / Activity 79 - Atlas of Portuguese Biosphere reserves | Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension | Output / Activity 81 - Itinerant exhibition | Custo total de despesas elegíveis / TOTAL ELIGIBLE BUDGET HEADING COSTS | % total custos elegíveis / % TOTAL ELIGIBLE COSTS
Cost of staff assigned to the project - Reg. Art. 8.3.1.a | 276435 | 4680 | 4500 | 8000 | 9568 | 2392 | 2392 | 8040 | 5780 | 1840 | 2392 | 0 | 0 | 2392 | 9568 | 19827.55 | 17264.15 | 6254.5 | 18572.53 | 18572.53 | 6840 | 26036.41 | 21669.32 | 22316.13 | 22663.26 | 17046.43 | 30402.44 | 10787.62 | 23676.35 | 17357.98 | 8722.52 | 5760 | 5220 | 5960 | 380 | 12307.86 | 9568 | 2392 | 5460 | 7500 | 12900 | 4360 | 7260 | 2392 | 5120 | 12064.14 | 19140 | 7260 | 9900 | 14740 | 36055.6 | 16137.99 | 17120.25 | 46736.82 | 5609.3 | 6827.9 | 8275 | 5612.5 | 9275 | 7400 | 6075 | 5312.5 | 5625 | 1887.5 | 1837.5 | 5437.5 | 1687.5 | 2625 | 2500 | 2625 | 2392 | 1228.3 | 360 | 7257.6 | 4581.67 | 500 | 3581.67 | 10400 | 21600 | 9568 | 32400 | 2392 | 1066596.82 | 48.51%
Travel and subsistence allowances for staff - Reg. Art. 8.3.1.b | 25693.11 | 0 | 7500 | 0 | 7900 | 0 | 9480 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3985 | 0 | 4283.8 | 953.52 | 953.52 | 6250 | 26186.52 | 0 | 0 | 16663.52 | 0 | 0 | 0 | 3985 | 13618 | 0 | 5000 | 4700 | 0 | 0 | 8567.6 | 53625 | 0 | 0 | 0 | 0 | 0 | 715.14 | 0 | 0 | 4422.18 | 4433.27 | 4033.27 | 4794.36 | 4225.7 | 1907.04 | 0 | 6035 | 4290.84 | 3800 | 0 | 7944.36 | 7829.75 | 1095.95 | 1095.95 | 438.38 | 0 | 0 | 0 | 5579.75 | 2991.9 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 0 | 0 | 0 | 7000 | 4422.18 | 4730 | 0 | 14410 | 0 | 299139.61 | 13.61%
Depreciation value for new or second hand equipment purchased - Reg. Art. 8.2.4 | 2902.5 | 56 | 110 | 88 | 0 | 0 | 0 | 84 | 62 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 90 | 64 | 2 | 0 | 0 | 0 | 50 | 168 | 140 | 48 | 46 | 0 | 54 | 0 | 174 | 56 | 70 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 4858.5 | 0.221%
Cost of new or second hand equipment - Reg. Art. 8.3.1.c & Art. 8.3.2 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9429.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19057.9 | 0.8668%
Purchase of land and real estate - Reg. Art. 8.3.1.d & Art. 8.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Costs of consumables and supplies - Reg. Art. 8.3.1.e | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 917.88 | 0 | 1500 | 3835.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 12453.64 | 0.5664%
Costs entailed by other contracts awarded by PP for the purpose of carrying out the project - Reg. Art. 8.3.1.f | 6493.86 | 0 | 0 | 0 | 9840 | 0 | 0 | 0 | 0 | 0 | 0 | 64575 | 24600 | 0 | 3690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44157 | 3690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 1000 | 4000 | 6400 | 9600 | 6400 | 84125 | 57625 | 16875 | 27625 | 20250 | 0 | 14550 | 14750 | 49750 | 0 | 0 | 0 | 0 | 0 | 4000 | 14000 | 0 | 0 | 3690 | 0 | 3690 | 535275.86 | 24.35%
Costs arising directly from requirements imposed by the project contract - Reg. Art. 8.3.1.g | 0 | 0 | 2075.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1729.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383.8 | 1107.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7264.95 | 0.3304%
INDIRECT COSTS - Reg. Art. 8.5 | [82 empty] | 254019.18 | 11.55%
TOTAL ELIGIBLE COSTS | 316524.47 | 4736 | 14185.7 | 8088 | 27308 | 2392 | 11872 | 8124 | 5842 | 1860 | 2392 | 64575 | 24600 | 2392 | 13258 | 28440.55 | 17264.15 | 10618.3 | 19526.05 | 19526.05 | 14945.75 | 53322.93 | 21669.32 | 22316.13 | 40426.78 | 26946.43 | 30402.44 | 10787.62 | 27661.35 | 30975.98 | 8722.52 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 116779.9 | 6082 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 2392 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 38880.52 | 16137.99 | 24655.25 | 54863.42 | 9409.3 | 36827.9 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 2392 | 1228.3 | 4960.66 | 7257.6 | 4581.67 | 4500 | 28581.67 | 14882.18 | 26330 | 13258 | 46810 | 6082 | 2198666.46
% TOTAL PROJECT COSTS | 14.4% | 0.2154% | 0.6452% | 0.3679% | 1.242% | 0.1088% | 0.54% | 0.3695% | 0.2657% | 0.0846% | 0.1088% | 2.937% | 1.119% | 0.1088% | 0.603% | 1.294% | 0.7852% | 0.4829% | 0.8881% | 0.8881% | 0.6798% | 2.425% | 0.9856% | 1.015% | 1.839% | 1.226% | 1.383% | 0.4906% | 1.258% | 1.409% | 0.3967% | 0.5588% | 0.5056% | 0.274% | 0.01737% | 0.9495% | 5.311% | 0.2766% | 0.2506% | 0.3488% | 0.5931% | 0.2005% | 0.3648% | 0.1088% | 0.2353% | 0.7498% | 1.08% | 0.5162% | 0.6715% | 0.8687% | 1.768% | 0.734% | 1.121% | 2.495% | 0.428% | 1.675% | 0.7832% | 0.7933% | 0.7628% | 0.823% | 0.5873% | 4.068% | 2.877% | 0.8534% | 1.594% | 1.304% | 0.07675% | 0.7812% | 0.7846% | 2.382% | 0.1088% | 0.05587% | 0.2256% | 0.3301% | 0.2084% | 0.2047% | 1.3% | 0.6769% | 1.198% | 0.603% | 2.129% | 0.2766% | 100%
Output / Activity Project Promoter / Partner | Management cost | Output /Activity 1 - Collection and organization of information related to the nomination of all Biosphere Reserves (BR) | Output / Activity 2 - Survey of existing BR action plans, objectives and priorities. | Output / Activity 3 - Framing the geostrategic context of BR in existing UNESCO BR networks | Output / Activity 4 - History of BR | Output / Activity 5 - Elaboration of a database management plan: FAIR data - open access | Output / Activity 6 - Auscultation / Perception and identification of heritage | Output / Activity 7 - Development of the Sustainable Development Plan (SDP) concept for BR | Output / Activity 8 - Development of the participatory planning methodology for the SDP | Output / Activity 9 - Consultation and validation of the methodological structure forthe SDP | Output / Activity 10 - Digital Infrastructure - distributed management model | Output / Activity 11 - Digital Infrastructure - Biosphere Reserves website | Output / Activity 12 - Digital infrastructure - Indicators management dashboard | Output / Activity 13 - Digital Infrastructure - Research Data Catalog | Output / Activity 14 - Digital guides to cultural and natural heritage of the Biosphere Reserves | Output / Activity 15 - Mapping the BR ecosystem diversity | Output / Activity 16 - Identification of potential Ecosystem Services (ES) associated with ecosystems | Output / Activity 17 - Analysis of the dynamics of the socio-economic sector | Output / Activity 18 - Identification of key actors in the socio-economic sector in the BR | Output / Activity 19 - Identification of existing R&DT, innovation and entrepreneurship best practices aligned with sustainable development | Output / Activity 20 - Identification of priorities and projects in the areas of development and sustainability | Output / Activity 21 - Selection of key ES for the sustainable development of BR | Output / Activity 22 - Selection of indicators and development of methodology for assessing the condition / status of ES | Output / Activity 23 - ES condition / status assessment | Output / Activity 24 - ES valuation proposal (add value) | Output / Activity 25 - ES valuation (assigning value) and its interconnection with the associated economic sectors - pilot action | Output / Activity 26 - Mapping BR ES | Output / Activity 27 - Proposal of management and conservation measures for BR and ES optimization | Output / Activity 28 - ES modeling to assess the effectiveness of management and conservation measures | Output / Activity 29 - Use of key ES in mitigation and adaptation to climate change in BR - pilot action | Output / Activity 30 - ES Sustainable Management Manual for BR | Output / Activity 31 - Elaboration and participative discussion of the Sustainable Development Plans (SDP) of each BR | Output / Activity 32 - SDP public presentations and discussions | Output / Activity 33 - Revision and editing of the final versions of the SDP | Output / Activity 34 - Selection of 11 pilot actions | Output / Activity 35 - Tourism "Script" for the Portuguese Biosphere Reserves - pilot action | Output / Activity 36 - Memories and identities - systematic record of memories | Output / Activity 37 - Creation of memory and community spaces - pilot action | Output / Activity 38 - Network of Biosphere Reserves shops and virtual store - pilot action | Output / Activity 39 - Benchmarking analysis of Sustainable Development (SD) indicators used in UNESCO's RB networks | Output / Activity 40 - Architecture of SDP indicators and monitoring system | Output / Activity 41 - Consultation and validation of the iSDP ndicators and monitoring system | Output / Activity 42 - Training of BR management teams and other stakeholders in the domain of the SDP Indicators and monitoring System | Output / Activity 43 - Citizen Science for sustainable BR - pilot action | Output / Activity 44 - Creation of the sustainable development barometer for Portuguese Biosphere Reserves | Output / Activity 45 - Sustainability certification framework - Portuguese Biosphere Reserves | Output / Activity 46 - Assessment of training needs that will support the training planing | Output / Activity 47 - Governance skills reinforcement program forBR managers, partners and local agents. | Output / Activity 48 - Training in planning and participatory methodologies for BR managers regarding the implementation of the SDP. | Output / Activity 49 - Training associated with the implementation of pilot actions | Output / Activity 50 - Training of local teams to support economic initiatives and funding opportunities | Output / Activity 51 - Capacitation of localBR decision makers in implementing the Sustainable Management Plans | Output / Activity 52 - Technical workshop on ecosystem services | Output / Activity 53 - Virtual incubation program in Portuguese Biosphere Reserves - pilot action | Output / Activity 54 - Program of visits and transfer of experiences between Portuguese BR and donor countries | Output / Activity 55 - Final project seminar | Output / Activity 56 - Marketing Strategy Development | Output / Activity 57 - Communication Plan Design | Output / Activity 58 - Strategy and Brand Identity (Tone, Signature and Communication Messages, Logo and Brandbook) | Output / Activity 59 - Generic Creative Development | Output / Activity 60 - Creative development of digital communication | Output / Activity 61 - Productions and promotional materials - Offline | Output / Activity 62 - Productions and promotional materials - Online | Output / Activity 63 - Productions and promotional materials - Audiovisual materials | Output / Activity 64 - Brand Activations | Output / Activity 65 - Public Relations | Output / Activity 66 - Media Strategy and Planning | Output / Activity 67 - Media Strategy and Planning - Press | Output / Activity 68 - Media Strategy and Planning - Radio | Output / Activity 69 - Media Strategy and Planning - Digital | Output / Activity 70 - Culture and Education Agenda | Output / Activity 71 - Development of Awareness Plan for different audiences | Output / Activity 72 - Local project presentation sessions in each Biosphere reserve including awareness and demonstration actions involving local partners | Output / Activity 73 - ES awareness actions | Output / Activity 74 - Planning of the National Biosphere Olympics | Output / Activity 75 - Communication and dissemination of the BR Olympics | Output / Activity 76 - BR Olympics | Output / Activity 77 - Design and organization of Biosphere Reserve Festivals | Output / Activity 78 - BioKeepers - Club of Friends and caregivers of RB | Output / Activity 79 - Atlas of Portuguese Biosphere reserves | Output / Atividade 80 - Extensão do conhecimento/ Activity 80 - Knowledge extension | Output / Activity 81 - Itinerant exhibition | TOTAL ELIGIBLE BUDGET HEADING COSTS | % TOTAL ELIGIBLE COSTS
Quaternaire Portugal, SA | 316524.47 | 4736 | 14185.7 | 8088 | 0 | 0 | 0 | 8124 | 5842 | 1860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10618.3 | 0 | 0 | 14945.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 0 | 0 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 0 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 0 | 0 | 0 | 0 | 4409.3 | 31827.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1228.3 | 4960.66 | 0 | 0 | 0 | 0 | 14882.18 | 0 | 0 | 0 | 0 | 622184.92 | 31.99%
Universidade de Coimbra | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21889.82 | 14698.42 | 0 | 0 | 0 | 0 | 41879.68 | 19103.59 | 19750.4 | 28983.53 | 26946.43 | 22004.71 | 10787.62 | 21110.62 | 28410.25 | 8722.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7740.26 | 10822.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7257.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290107.97 | 14.92%
Universidade Nova de Lisboa | 0 | 0 | 0 | 0 | 27308 | 2392 | 11872 | 0 | 0 | 0 | 2392 | 64575 | 24600 | 2392 | 13258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116779.9 | 6082 | 0 | 0 | 0 | 0 | 0 | 2392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13258 | 0 | 6082 | 295774.9 | 15.21%
PC&A - Consultores de Marketing Estratégico, Lda | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406101.04 | 20.88%
Instituto Pedro Nunes, AIDCT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19526.05 | 19526.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38880.52 | 0 | 0 | 54863.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132796.04 | 6.829%
Ordem dos Biólogos | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4581.67 | 4500 | 28581.67 | 0 | 0 | 0 | 0 | 0 | 37663.34 | 1.937%
KEEP - Knowledge for Peace, People and the Planet, Association | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26330 | 0 | 46810 | 0 | 73140 | 3.761%
University of Bergen | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6550.73 | 2565.73 | 0 | 0 | 0 | 0 | 2565.73 | 2565.73 | 2565.73 | 2565.73 | 0 | 2565.73 | 0 | 6550.73 | 2565.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565.73 | 6550.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40178.03 | 2.066%
Nordhordland Utviklingsselskap IKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8877.52 | 0 | 0 | 8877.52 | 0 | 5832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5832 | 7282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36701.04 | 1.887%
Icelandic National Commission for UNESCO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 0.5142%
TOTAL ELIGIBLE COSTS | 316524.47 | 4736 | 14185.7 | 8088 | 27308 | 2392 | 11872 | 8124 | 5842 | 1860 | 2392 | 64575 | 24600 | 2392 | 13258 | 28440.55 | 17264.15 | 10618.3 | 19526.05 | 19526.05 | 14945.75 | 53322.93 | 21669.32 | 22316.13 | 40426.78 | 26946.43 | 30402.44 | 10787.62 | 27661.35 | 30975.98 | 8722.52 | 12285.8 | 11117.04 | 6024 | 382 | 20875.46 | 116779.9 | 6082 | 5510 | 7668 | 13040 | 4408 | 8021.14 | 2392 | 5174 | 16486.32 | 23747.27 | 11349.27 | 14764.36 | 19099.7 | 38880.52 | 16137.99 | 24655.25 | 54863.42 | 9409.3 | 36827.9 | 17219.36 | 17442.25 | 16770.95 | 18095.95 | 12913.38 | 89437.5 | 63250 | 18762.5 | 35042.25 | 28679.4 | 1687.5 | 17175 | 17250 | 52375 | 2392 | 1228.3 | 4960.66 | 7257.6 | 4581.67 | 4500 | 28581.67 | 14882.18 | 26330 | 13258 | 46810 | 6082 | 1944647.28
* SEE 9.ELIGIBILITY OF EXPENDITURE ; **SEE 16. ADDITIONAL INFORMATION

## Budget_year
Programme: | Environment, Climate Change and Low Carbon Economy Programme
Project title: | Biosphere Reserves: sustainable territories, resilient communities
Project Promoter: | Quaternaire Portugal, SA
Total project cost: | 2198666.46
Project grant rate: | 100%
Project duration: | 30 months
Year Project Promoter/ Partner | Year 1 | Year 2 | Year 3 | TOTAL
Quaternaire Portugal, SA | 289113.8102 | 293623.8901 | 140385.8897 | 723123.59
Universidade de Coimbra | 130726.832 | 151014.8888 | 41501.6891 | 323243.41
Universidade Nova de Lisboa | 255922.08 | 86225.4 | 12782.4 | 354929.88
PC&A - Consultores de Marketing Estratégico, Lda | 91071.7845 | 280433.4652 | 53226.0003 | 424731.25
Instituto Pedro Nunes, AIDCT | 46862.5206 | 112492.7294 | 0 | 159355.25
Ordem dos Biólogos | 14976.0089 | 24420.0011 | 0 | 39396.01
KEEP - Knowledge for Peace, People and the Planet, Association | 32094 | 27364 | 13682 | 73140
University of Bergen | 18893.3794 | 18151.0279 | 11169.6226 | 48214.03
Nordhordland Utviklingsselskap IKS | 13858.6012 | 14634.1248 | 14040.314 | 42533.04
Icelandic National Commission for UNESCO | 0 | 3440.208 | 6559.792 | 10000
TOTAL ELIGIBLE COSTS | 893519.0168 | 1011799.7353 | 293347.7078 | 2198666.46
% TOTAL PROJECT COSTS | 40.64% | 46.02% | 13.34%